## Sheet1
Step | Description | Dependent on Step | Duration from prev Step
1 | SRF Submitted
2 | Initial Review | 1 | +1 | First planned date is forecasted on SRF Submitted Actual Date
3 | Space Check | 2 | +2
3 | Facilities Check | 2 | +2
3 | Estates Check | 2 | +2
3 | Customer Accounts Check | 2 | +2
4 | Towercom Response (Feedback) | 3 | +2 | Option to Feedback/Approve - 'Approved' completes Step 8 also.
5 | SRF Resubmitted | 4 |  | Dependent on whether Step 4 is 'Feedback' or 'Approved'.
6 | Space Check | 5 | +2 | Planned dates forecasted on SRF Resubmitted Actual Date
6 | Facilities Check | 5 | +2
6 | Estates Check | 5 | +2
6 | Customer Accounts Check | 5 | +2
7 | TL Drawing Uploaded | 3 or 6 | +2 | Depended on whether TL Drawing required Y/N in Initial Review
8 | SRF Approved | 3 or 6 | +2 | When Step 4 is Approved not Feedback.
9 | Customer Accepted/Licence Requested | 8 | +2
10a | SDS Pack Produced | 9 | +2
11a | SDS Pack Reviewed/Issued | 9 | +2
11b | SDS Signed | 11a | +5
11c | SDS Executed | 11b | +1
12 | Works Permitted | ??? |  | Can be actioned any time after Step 9 so not sure how to forecast