## TimeEntries
Internal ID | Date | Employee | Item | Duration | Approval Status | Case/Task/Event | Billable | Date Created | Formula (Text) | Charge Billing Run ID
1542360 | 2026-09-04 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-09-07 | Updates to Saved Searches and Reports?Custom centre tab and category for SS and Reports
1542357 | 2026-09-03 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Stationery (Project Task) | Yes | 2026-09-07 | Updates to Sales Invoice PDF
1542362 | 2026-09-03 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : E-Payments (Project Task) | Yes | 2026-09-07 | EFT file testing with AIB and code changes to format?Finance Checklist tasks
1542359 | 2026-09-02 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-09-07 | Updates to Saved Searches and Reports?Custom centre tab and category for SS and Reports
1542358 | 2026-09-01 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-09-07 | Updates to roles for Finance
1542361 | 2026-09-01 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : E-Payments (Project Task) | Yes | 2026-09-07 | EFT file testing with AIB and code changes to format?Finance Checklist tasks
1541950 | 2026-08-31 | Giuseppe Dev | SRConNS | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list fixing SRF saving issue session with Laco
1541868 | 2026-08-31 | Ladislav Zimanyi | SRDevNSFOC | 3 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-31 | Towercom - dev session with Giuseppe
1542028 | 2026-08-31 | Dave O'Hanlon | SRConPMNS | 1 | Approved | Project Management (Project Task) | No | 2026-09-01 | Updates to actions checklist
1541949 | 2026-08-28 | Giuseppe Dev | SRConNS | 5.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list
1541595 | 2026-08-28 | Ladislav Zimanyi | SRDevNSFOC | 2 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-28 | Towercom - session with Jesna - overview and session with Amy on Nexus process
1541722 | 2026-08-28 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-28 | Working with Towercom Finance to train ahead of Go-Live?Finance actions
1541703 | 2026-08-28 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-08-28 | Roles and moving to prod
1541717 | 2026-08-28 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Stationery (Project Task) | Yes | 2026-08-28 | Work on Towercom Invoice PDF
1541948 | 2026-08-27 | Giuseppe Dev | SRConNS | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list
1541590 | 2026-08-27 | Ladislav Zimanyi | SRDevNSFOC | 1 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-28 | Towercom - session with Amy & Bogdan on FS app /// Towercom - meetings with development
1541721 | 2026-08-27 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-28 | Working with Towercom Finance to train ahead of Go-Live?Finance actions
1541718 | 2026-08-27 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : E-Payments (Project Task) | Yes | 2026-08-28 | Work on testing electronic payments?File format additions
1541947 | 2026-08-26 | Giuseppe Dev | SRConNS | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | fixing issue with Saving big SRFs
1541720 | 2026-08-26 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-28 | Working with Towercom Finance to train ahead of Go-Live?Finance actions
1541946 | 2026-08-25 | Giuseppe Dev | SRConNS | 2.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list planning / onborading (claude) and other managment tasks
1541589 | 2026-08-25 | Ladislav Zimanyi | SRDevNSFOC | 0.5 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-28 | Towercom - session with Amy & Bogdan on FS app /// Towercom - meetings with development
1541719 | 2026-08-25 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-28 | Working with Towercom Finance to train ahead of Go-Live?Finance actions
1541702 | 2026-08-24 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-08-28 | Imports for Nexus
1541926 | 2026-08-21 | Giuseppe Dev | SRConNS | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list review few issues with Laco review issue list with laco fsa app :: issue with login
1541440 | 2026-08-21 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-08-26 | Work on go-live finance actions
1541435 | 2026-08-21 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-26 | Finalised Production Data Imports
1541925 | 2026-08-20 | Giuseppe Dev | SRConNS | 4.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list
1540733 | 2026-08-20 | Ladislav Zimanyi | SRDevNSFOC | 1 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-22 | Towercom - Check on issues with GG and meeting with Amy/Anna.
1541439 | 2026-08-20 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-08-26 | Work on go-live finance actions
1541434 | 2026-08-20 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-26 | Finalised Production Data Imports
1541927 | 2026-08-19 | Giuseppe Dev | SRConNS | 0.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | call with Laco
1541438 | 2026-08-19 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-08-26 | Work on go-live finance actions
1541433 | 2026-08-19 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-26 | Finalised Production Data Imports
1541924 | 2026-08-18 | Giuseppe Dev | SRConNS | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list FSA session with Laco
1540731 | 2026-08-18 | Ladislav Zimanyi | SRDevNSFOC | 1 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-22 | Towercom - form builder crash course with GG
1541437 | 2026-08-18 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-08-26 | Work on go-live finance actions
1541432 | 2026-08-18 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-26 | Finalised Production Data Imports
1541431 | 2026-08-17 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-26 | Finalised Production Data Imports
1541436 | 2026-08-17 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-08-26 | Work on go-live finance actions
1540346 | 2026-08-14 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Stationery (Project Task) | Yes | 2026-08-18 | Updates to PO PDF?Updates to Invoice PDF?Updates to Towercom Transaction Forms?Import of Open Transactions to Prod
1541673 | 2026-08-14 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-08-28 | Imports and moving roles to live
1540351 | 2026-08-14 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-18 | Towecom Action Items to get Finance Live
1541907 | 2026-08-13 | Giuseppe Dev | SRConNS | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list
1540120 | 2026-08-13 | Ladislav Zimanyi | SRDevNSFOC | 1 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-14 | Towercom - testing support
1540127 | 2026-08-13 | Ladislav Zimanyi | SRDevNSFOC | 1 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-14 | Towercom - meeting with Anna and liaise with GG on few issues /// Meeting with Towercome - review
1541672 | 2026-08-13 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-08-28 | Imports and moving roles to live
1540350 | 2026-08-13 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-18 | Towecom Action Items to get Finance Live
1540345 | 2026-08-13 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Stationery (Project Task) | Yes | 2026-08-18 | Updates to PO PDF?Updates to Invoice PDF?Updates to Towercom Transaction Forms?Import of Open Transactions to Prod
1540344 | 2026-08-12 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Stationery (Project Task) | Yes | 2026-08-18 | Updates to PO PDF?Updates to Invoice PDF?Updates to Towercom Transaction Forms?Import of Open Transactions to Prod
1540126 | 2026-08-12 | Ladislav Zimanyi | SRDevNSFOC | 2 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-14 | Towercom - meeting with Anna and liaise with GG on few issues /// Meeting with Towercome - review
1540349 | 2026-08-12 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-18 | Towecom Action Items to get Finance Live
1541908 | 2026-08-11 | Giuseppe Dev | SRConNS | 0.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | review list with Laco
1540119 | 2026-08-11 | Ladislav Zimanyi | SRDevNSFOC | 2 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-14 | Towercom - testing support
1540348 | 2026-08-11 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-18 | Towecom Action Items to get Finance Live
1540343 | 2026-08-11 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Stationery (Project Task) | Yes | 2026-08-18 | Updates to PO PDF?Updates to Invoice PDF?Updates to Towercom Transaction Forms?Import of Open Transactions to Prod
1541906 | 2026-08-10 | Giuseppe Dev | SRConNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list review list with Laco
1540347 | 2026-08-10 | Dave O'Hanlon | SRConNS | 1.75 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-08-18 | Import of Open Transactions to Prod
1540342 | 2026-08-10 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Stationery (Project Task) | Yes | 2026-08-18 | Updates to PO PDF?Updates to Invoice PDF?Updates to Towercom Transaction Forms?Import of Open Transactions to Prod
1541887 | 2026-08-07 | Giuseppe Dev | SRConNS | 2.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | issue list
1539756 | 2026-08-07 | Ladislav Zimanyi | SRDevNSFOC | 2 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-07 | Towercom - Liaiase/support with Mark and GG on few small issues /// Towercom - testing support + liaise with GG
1539766 | 2026-08-07 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-08-07 | Update Purchase transactions Jan - Apr in Prod for VAT3 checking, response to emails, work on action items
1541886 | 2026-08-06 | Giuseppe Dev | SRConNS | 4.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | SRF dashboards SRF Library tweaks helping laco issue list
1539755 | 2026-08-06 | Ladislav Zimanyi | SRDevNSFOC | 2 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-07 | Towercom - Liaiase/support with Mark and GG on few small issues /// Towercom - testing support + liaise with GG
1539767 | 2026-08-06 | Dave O'Hanlon | SRConNS | 6 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-08-07 | Towercom Onsite?Purchase Review?Sales Review
1541885 | 2026-08-05 | Giuseppe Dev | SRConNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | fixing couple of issues with Laco handling Voltage Tupe/Range list change to custom record issue / feedback list fixing uregent issues for Amy
1539754 | 2026-08-05 | Ladislav Zimanyi | SRDevNSFOC | 4 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-07 | Towercom - Liaiase/support with Mark and GG on few small issues /// Towercom - testing support + liaise with GG
1539765 | 2026-08-05 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-08-07 | Update Purchase transactions Jan - Apr in Prod for VAT3 checking, response to emails, work on action items
1541884 | 2026-08-04 | Giuseppe Dev | SRConNS | 2.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-09-01 | SRF fixing issue on company profile screen
1539753 | 2026-08-04 | Ladislav Zimanyi | SRDevNSFOC | 2 | Approved | Development Project Mgt - Ladislav (Project Task) | No | 2026-08-07 | Towercom - Liaiase/support with Mark and GG on few small issues /// Towercom - testing support + liaise with GG
1541628 | 2026-08-04 | Sean Munroe | SRConNS | 8 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-08-28 | Field App, User Access, roles permissions and UAT issues
1538661 | 2026-08-03 | Sean Munroe | SRConNS | 0 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | No | 2026-07-27 | Scheduled via PM Dashboard
1539342 | 2026-07-31 | Giuseppe Dev | SRDevOSSMSpace | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | TODO List issue list
1538844 | 2026-07-30 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-07-29 | Finance Items: Custom Forms, Fields, Workflows, Scripting, Saved Searches, Reports?Historical Imports?Project Imports
1539341 | 2026-07-30 | Giuseppe Dev | SRDevOSSMSpace | 9.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SDS and related stuff SAF fixes issue list SRF / SAF Tweaks TODO List
1538843 | 2026-07-29 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-07-29 | Finance Items: Custom Forms, Fields, Workflows, Scripting, Saved Searches, Reports?Historical Imports?Project Imports
1539340 | 2026-07-29 | Giuseppe Dev | SRDevOSSMSpace | 6.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SDS SDS Items session with customer post meeting
1538656 | 2026-07-28 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-07-27 | UAT Issue List and roles
1539339 | 2026-07-28 | Giuseppe Dev | SRDevOSSMSpace | 9.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | issue list claring @@TODO tags SRF / SDF / SAF SDS PDF and other bits SDS Conditions Equip. Lib Config :: review with Laco
1538659 | 2026-07-28 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-07-27 | Finance Items: Custom Forms, Fields, Workflows, Scripting, Saved Searches, Reports?Historical Imports?Project Imports
1538660 | 2026-07-27 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-07-27 | Finance Items: Custom Forms, Fields, Workflows, Scripting, Saved Searches, Reports?Historical Imports?Project Imports
1539338 | 2026-07-27 | Giuseppe Dev | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SAF / SDS issue list post meeting session with customer
1538655 | 2026-07-27 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Advance Reporting and KPI (Project Task) | Yes | 2026-07-27 | UAT Issue List and roles
1539244 | 2026-07-26 | Giuseppe Dev | SRDevOSSMSpace | 7 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SAF / SDS
1539243 | 2026-07-25 | Giuseppe Dev | SRDevOSSMSpace | 6.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SAF / SDS
1538596 | 2026-07-24 | Sean Munroe | SRConNS | 5 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-24 | Customising forms, Changes to the Schemas and importing of data into production
1539242 | 2026-07-24 | Giuseppe Dev | SRDevOSSMSpace | 6.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SAF / SDS dev meeting
1538704 | 2026-07-24 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538702 | 2026-07-24 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538697 | 2026-07-24 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538595 | 2026-07-23 | Sean Munroe | SRConNS | 5 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-24 | Customising forms, Changes to the Schemas and importing of data into production
1539241 | 2026-07-23 | Giuseppe Dev | SRDevOSSMSpace | 4.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SDS
1538696 | 2026-07-23 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538695 | 2026-07-22 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1539240 | 2026-07-22 | Giuseppe Dev | SRDevOSSMSpace | 5.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SDS
1538653 | 2026-07-22 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-26 | - Worked on Resolving Towercom Issue Tickets.
1538703 | 2026-07-22 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538701 | 2026-07-22 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538594 | 2026-07-21 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-07-24 | Moving roles to Production and testing
1539239 | 2026-07-21 | Giuseppe Dev | SRDevOSSMSpace | 2.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SDS
1538700 | 2026-07-21 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538694 | 2026-07-21 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538593 | 2026-07-20 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-07-24 | Moving roles to Production and testing
1539238 | 2026-07-20 | Giuseppe Dev | SRDevOSSMSpace | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | SRF / SDS dev meeting
1538108 | 2026-07-20 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-14 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538699 | 2026-07-20 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-07-27 | Towercom Importing Project and Transactional Date?Testing of Finance processes and updates to functionality?Meetings with Towercom
1538215 | 2026-07-17 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-07-17 | Importing Bank Transactions?Update project records in SB?Update Journals in Prod?Created JE approval WF
1539124 | 2026-07-17 | Giuseppe Dev | SRDevOSSMSpace | 1.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | resume project (back from holiday)
1538064 | 2026-07-17 | Sean Munroe | SRConNS | 8 | Approved | Consultancy : Stationery (Project Task) | Yes | 2026-07-14 | Roles schema changes and imports
1538061 | 2026-07-16 | Sean Munroe | SRConNS | 8 | Approved | Consultancy : Test Production (Project Task) | Yes | 2026-07-14 | Working through roles and Issue List
1539126 | 2026-07-16 | Giuseppe Dev | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | resume project meeting (back from holiday)
1539125 | 2026-07-15 | Giuseppe Dev | SRDevOSSMSpace | 0.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-07-31 | resume project (back from holiday)
1538202 | 2026-07-15 | Jesna John | SRDevOSSMSpace | 2 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-17 | Worked on issue tickets for Towercom related to displaying some script errors while trying to create the SAF and clicking on new SAF button.
1538070 | 2026-07-14 | Dave O'Hanlon | SRConNS | 5 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-07-14 | Importing Bank Transactions?Update project records in SB?Update Journals in Prod?Created JE approval WF
1538046 | 2026-07-13 | Dave O'Hanlon | SRConNS | 6 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-13 | Towercom Projects - created new lists, updated custom segment and import to Production
1538313 | 2026-07-13 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-19 | - Worked on Towercom Issue Tickets
1537833 | 2026-07-10 | Sean Munroe | SRConNS | 5.5 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-10 | Creating Tables and moving these and fields across to production for custom records for imports.?Import of Companies, Profiles, ACL and ASCL
1537868 | 2026-07-10 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-12 | - Worked on Kizeo Forms to implement custom record creation and map form fields accordingly.?- Worked on Towercom issue tickets and resolved two tickets. ?- Worked on Towercom issue tickets and resolved 3 tickets.
1537895 | 2026-07-09 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Test Production (Project Task) | Yes | 2026-07-13 | Ensuring VAT3 is setup for Towercom tax returns
1537832 | 2026-07-09 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-10 | Creating Tables and moving these and fields across to production for custom records for imports.?Import of Companies, Profiles, ACL and ASCL
1537896 | 2026-07-09 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-13 | Created custom fields, editing forms in production. Projects Call with Towercom
1537672 | 2026-07-08 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-09 | Created custom fields, editing forms in production. Projects Call with Towercom
1537754 | 2026-07-08 | Jesna John | SRDevOSSMSpace | 1 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-10 | Working on FSA forms, custom record creation and binding of the forms with the fields. Issue tickets resolved. checked the issue for checkbox setting.
1537831 | 2026-07-08 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-10 | Creating Tables and moving these and fields across to production for custom records for imports.?Import of Companies, Profiles, ACL and ASCL
1537673 | 2026-07-07 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Workflow (Project Task) | Yes | 2026-07-09 | Workflows copied to Prodcution
1537867 | 2026-07-07 | Javeed Shabeer | SRDevOSSMSpace | 3 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-12 | - Worked on Kizeo Forms to implement custom record creation and map form fields accordingly.?- Worked on Towercom issue tickets and resolved two tickets. ?- Worked on Towercom issue tickets and resolved 3 tickets.
1537830 | 2026-07-07 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-10 | Creating Tables and moving these and fields across to production for custom records for imports.?Import of Companies, Profiles, ACL and ASCL
1537670 | 2026-07-06 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Test Production (Project Task) | Yes | 2026-07-09 | Ensuring VAT3 is setup for Towercom tax returns
1537753 | 2026-07-06 | Jesna John | SRDevOSSMSpace | 3 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-10 | Working on FSA forms, custom record creation and binding of the forms with the fields. Issue tickets resolved. checked the issue for checkbox setting.
1537829 | 2026-07-06 | Sean Munroe | SRConNS | 2.5 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-10 | Creating Tables and moving these and fields across to production for custom records for imports.?Import of Companies, Profiles, ACL and ASCL
1537671 | 2026-07-06 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-09 | Created custom fields, editing forms in production. Projects Call with Towercom
1537417 | 2026-07-03 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-06 | VAT Reconciliation working in SB
1537325 | 2026-07-03 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-03 | - Worked on Kizeo Forms to implement custom record creation and map form fields accordingly.?- Worked on Kizeo forms to mapping the fields from the custom records.?- Worked on Towercom issue tickets.
1537319 | 2026-07-03 | Jesna John | SRDevOSSMSpace | 5 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-03 | Working on FSA Forms and Custom record creation, Binding forms to custom record fields.
1537801 | 2026-07-03 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-07-10 | Setting up Roles and Custom Centers?reviewing issues list
1537420 | 2026-07-03 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-06 | Towercom Items import?Towercom Class import?Set up tax codes and schedules
1537416 | 2026-07-02 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-06 | VAT Reconciliation working in SB
1537324 | 2026-07-02 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-03 | - Worked on Kizeo Forms to implement custom record creation and map form fields accordingly.?- Worked on Kizeo forms to mapping the fields from the custom records.?- Worked on Towercom issue tickets.
1537800 | 2026-07-02 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-07-10 | Setting up Roles and Custom Centers?reviewing issues list
1537419 | 2026-07-02 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-06 | Towercom Items import?Towercom Class import?Set up tax codes and schedules
1537415 | 2026-07-01 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-07-06 | VAT Reconciliation working in SB
1537318 | 2026-07-01 | Jesna John | SRDevOSSMSpace | 6 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-07-03 | Working on FSA Forms and Custom record creation, Binding forms to custom record fields.
1537423 | 2026-07-01 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-07-06 | TWCM - Accountant role setup and testing for Finance team
1537418 | 2026-07-01 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-07-06 | Towercom Items import?Towercom Class import?Set up tax codes and schedules
1537036 | 2026-06-30 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Workflow (Project Task) | Yes | 2026-06-30 | VB Approval Workflow setup in SB
1537050 | 2026-06-30 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-30 | - Worked on Kizeo Forms to implement custom record creation and map form fields accordingly.?- Worked on Kizeo forms to mapping the fields from the custom records.?- Worked on Towercom issue tickets.
1536989 | 2026-06-30 | Jesna John | SRDevOSSMSpace | 3 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-30 | Working on FSA Forms and Custom record creation, Binding forms to custom record fields.
1536817 | 2026-06-30 | Anna Carolan | SRConPMNS | 8 | Approved | Project Management (Project Task) | No | 2026-06-29 | Opening Balances
1537038 | 2026-06-30 | Dave O'Hanlon | SRConNS | 5 | Approved | Consultancy : Test Production (Project Task) | Yes | 2026-06-30 | Moving config from SB to Production and reconcilliation
1537037 | 2026-06-29 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : Test Production (Project Task) | Yes | 2026-06-30 | Moving config from SB to Production and reconcilliation
1537049 | 2026-06-29 | Javeed Shabeer | SRDevOSSMSpace | 1 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-30 | - Worked on Kizeo Forms to implement custom record creation and map form fields accordingly.?- Worked on Kizeo forms to mapping the fields from the custom records.?- Worked on Towercom issue tickets.
1536988 | 2026-06-29 | Jesna John | SRDevOSSMSpace | 4 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-30 | Working on FSA Forms and Custom record creation, Binding forms to custom record fields.
1536721 | 2026-06-26 | Sean Munroe | SRConNS | 5 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-06-26 | Setting up Netsuite roles and permissions for Towercom nexus users and reviewing issues list
1536779 | 2026-06-26 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-28 | - Worked on Keizo forms and completed the creation of the required forms.
1536689 | 2026-06-26 | Jesna John | SRDevOSSMSpace | 4 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-26 | Worked on FSA forms.
1536618 | 2026-06-26 | Giuseppe Dev | SRDevOSSMSpace | 2.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | dasta import meeting + issue lists
1537019 | 2026-06-26 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-06-30 | Opening Balance TBs Import to Production
1537016 | 2026-06-26 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-30 | Building Production for Go Live - CoA, Vendors, Cutomers
1536720 | 2026-06-25 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-06-26 | Setting up Netsuite roles and permissions for Towercom nexus users and reviewing issues list
1536778 | 2026-06-25 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-28 | - Worked on Keizo forms and completed the creation of the required forms.
1536688 | 2026-06-25 | Jesna John | SRDevOSSMSpace | 4 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-26 | Worked on FSA forms.
1537018 | 2026-06-25 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-06-30 | Opening Balance TBs Import to Production
1537015 | 2026-06-25 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-30 | Building Production for Go Live - CoA, Vendors, Cutomers
1537014 | 2026-06-24 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-30 | Building Production for Go Live - CoA, Vendors, Cutomers
1536616 | 2026-06-24 | Giuseppe Dev | SRDevOSSMSpace | 1.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | call with Team
1537017 | 2026-06-24 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Workflow (Project Task) | Yes | 2026-06-30 | PO approval Workflow in SB
1537013 | 2026-06-23 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-30 | Building Production for Go Live - CoA, Vendors, Cutomers
1536617 | 2026-06-23 | Giuseppe Dev | SRDevOSSMSpace | 1.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | internal meeting
1537012 | 2026-06-22 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-30 | Building Production for Go Live - CoA, Vendors, Cutomers
1536777 | 2026-06-22 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-28 | - Worked on Keizo forms and completed the creation of the required forms.
1536615 | 2026-06-22 | Giuseppe Dev | SRDevOSSMSpace | 4.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | OSSMTWC + OSSSMFSA :: full live dployment
1536706 | 2026-06-19 | Sean Munroe | SRConNS | 6 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-06-26 | Working through UAT issues list, roles and permissions . Kezio forms, Field App and workflows
1536596 | 2026-06-19 | Giuseppe Dev | SRDevOSSMSpace | 5.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | SRF Workflow
1536286 | 2026-06-19 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-19 | Configuration of Production for Go-Live - Subs, CoA, Features, Lists
1536698 | 2026-06-18 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-06-26 | SRF process and workflow
1536595 | 2026-06-18 | Giuseppe Dev | SRDevOSSMSpace | 6 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | SRF Workflow SRF Workflow Meeting with client call with Anna
1536285 | 2026-06-18 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-19 | Configuration of Production for Go-Live - Subs, CoA, Features, Lists
1536705 | 2026-06-18 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-06-26 | Working through UAT issues list, roles and permissions . Kezio forms, Field App and workflows
1536284 | 2026-06-17 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-19 | Configuration of Production for Go-Live - Subs, CoA, Features, Lists
1536214 | 2026-06-17 | Javeed Shabeer | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-19 | - Worked on the Towercom Print SDS to add the Details of Parties table data
1536594 | 2026-06-17 | Giuseppe Dev | SRDevOSSMSpace | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | SRF Workflow Preparing for Laco briefing internal meeting
1536808 | 2026-06-16 | Anna Carolan | SRConPMNS | 8 | Approved | Project Management (Project Task) | No | 2026-06-29 | Opening Balances
1536807 | 2026-06-15 | Anna Carolan | SRConPMNS | 8 | Approved | Project Management (Project Task) | No | 2026-06-29 | Opening Balances
1536593 | 2026-06-15 | Giuseppe Dev | SRDevOSSMSpace | 6.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | SRF Workflow session with Sean :: FSA Forms + Issue List call with Laco about project managing the project
1536578 | 2026-06-14 | Giuseppe Dev | SRDevOSSMSpace | 7.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | SRF Entry SRF Workflow
1536577 | 2026-06-13 | Giuseppe Dev | SRDevOSSMSpace | 6.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | SRF Workflow
1535804 | 2026-06-12 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-06-12 | working through issues list, Projects, Trouble tickets Jobs and Cases and field App. SDS
1535838 | 2026-06-12 | Javeed Shabeer | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-12 | - Worked on Towercom Kezio form for creating using Form Builder.?- Worked on Towercom Print SDS to add the Details of Parties.?- Worked on Towercom issue tickets.?- Resolved some issue on Towercom ticket (33).?- Attended Towercom testing update call for resolving an issue.
1536576 | 2026-06-12 | Giuseppe Dev | SRDevOSSMSpace | 6.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | SRF Entry
1536806 | 2026-06-12 | Anna Carolan | SRConNS | 8 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-06-29 | Opening Balances
1535814 | 2026-06-12 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-06-12 | Reviewing Docs on roles permissions and start creation of Netsuite roles
1535803 | 2026-06-11 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-06-12 | working through issues list, Projects, Trouble tickets Jobs and Cases and field App. SDS
1536579 | 2026-06-11 | Giuseppe Dev | SRDevOSSMSpace | 0.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | call with Anna
1535837 | 2026-06-11 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-12 | - Worked on Towercom Kezio form for creating using Form Builder.?- Worked on Towercom Print SDS to add the Details of Parties.?- Worked on Towercom issue tickets.?- Resolved some issue on Towercom ticket (33).?- Attended Towercom testing update call for resolving an issue.
1535785 | 2026-06-11 | Abin Pious | SRDevOSSMSpace | 1 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-12 | Changes on app for holiday and timesheet.
1535836 | 2026-06-09 | Javeed Shabeer | SRDevOSSMSpace | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-12 | - Worked on Towercom Kezio form for creating using Form Builder.?- Worked on Towercom Print SDS to add the Details of Parties.?- Worked on Towercom issue tickets.?- Resolved some issue on Towercom ticket (33).?- Attended Towercom testing update call for resolving an issue.
1535802 | 2026-06-08 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-06-12 | working through issues list, Projects, Trouble tickets Jobs and Cases and field App. SDS
1535835 | 2026-06-08 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-12 | - Worked on Towercom Kezio form for creating using Form Builder.?- Worked on Towercom Print SDS to add the Details of Parties.?- Worked on Towercom issue tickets.?- Resolved some issue on Towercom ticket (33).?- Attended Towercom testing update call for resolving an issue.
1535784 | 2026-06-08 | Abin Pious | SRDevOSSMSpace | 3 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-12 | Changes on app for holiday and timesheet.
1535847 | 2026-06-05 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-06-12 | Kezio Forms
1535572 | 2026-06-05 | Javeed Shabeer | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-05 | - Developed a pop-up screen to capture manual details and include them in the generated PDF, and created a preview screen to display the manually entered information.
1535846 | 2026-06-04 | Sean Munroe | SRConNS | 6 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-06-12 | SRF Workflow Trouble tickets and field App walkthrough?SDS Configuration and testing
1536557 | 2026-06-04 | Giuseppe Dev | SRDevOSSMSpace | 2.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-26 | srf workflow meeting call with Ray & Carlos & Dawn
1535571 | 2026-06-04 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-05 | - Developed a pop-up screen to capture manual details and include them in the generated PDF, and created a preview screen to display the manually entered information.
1535553 | 2026-06-04 | Abin Pious | SRDevOSSMSpace | 4 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-05 | Expense and time pages for towercom app.
1535552 | 2026-06-03 | Abin Pious | SRDevOSSMSpace | 8 | Approved | Development : Schedular and Holiday tracker - Phase 2 (Project Task) | No | 2026-06-05 | Expense and time pages for towercom app.
1535570 | 2026-06-03 | Javeed Shabeer | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-05 | - Developed a pop-up screen to capture manual details and include them in the generated PDF, and created a preview screen to display the manually entered information.
1535845 | 2026-06-02 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-06-12 | SRF Workflow Trouble tickets and field App walkthrough?SDS Configuration and testing
1535569 | 2026-06-02 | Javeed Shabeer | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-06-05 | - Developed a pop-up screen to capture manual details and include them in the generated PDF, and created a preview screen to display the manually entered information.
1535056 | 2026-05-29 | Sean Munroe | SRConNS | 5 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-05-29 | Working through requirements for SDS, Roles, Templates for imports and UAT list of issues
1535055 | 2026-05-28 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-05-29 | Working through requirements for SDS, Roles, Templates for imports and UAT list of issues
1534631 | 2026-05-27 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-05-27 | Meeting with Grainne and Karen re Finance actvities
1534781 | 2026-05-26 | Giuseppe Dev | SRDevNS | 0.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-29 | SRF Workflow call
1534626 | 2026-05-25 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-27 | - Worked on the Towercom Company Profile by adding a new column to the Company Profile List (The field could not be added as the field type was multiselect and that needs to be configured).?- Worked on adding the “Agent Passes” column to the Profile custom record, where the field belonged to a different List/Record type (waiting for the Sean's input on this).
1534254 | 2026-05-22 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-05-22 | Reviewing Custom Records and prepping Templates for go live
1534279 | 2026-05-22 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-22 | - Worked on creating the PDF for SRF screen, and worked on couple of issues related to Towercom.
1534763 | 2026-05-21 | Giuseppe Dev | SRDevNS | 0.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-29 | call with Anna, Carlos
1534278 | 2026-05-21 | Javeed Shabeer | SRDevOSSMSpace | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-22 | - Worked on creating the PDF for SRF screen, and worked on couple of issues related to Towercom.
1534253 | 2026-05-21 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-05-22 | Reviewing Custom Records and prepping Templates for go live
1534277 | 2026-05-20 | Javeed Shabeer | SRDevOSSMSpace | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-22 | - Worked on creating the PDF for SRF screen, and worked on couple of issues related to Towercom.
1534762 | 2026-05-19 | Giuseppe Dev | SRDevNS | 1.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-29 | dev meeting call with Anna, Carlos and Ray
1534748 | 2026-05-15 | Giuseppe Dev | SRDevNS | 0.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-29 | weekly internal meeting
1533590 | 2026-05-15 | Jesna John | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-15 | Worked on issue tickets. Worked on Towercom to-dos for dispalying table for uploaded images, adding separate sections for open images uploaded in trouble tickets.?Created user event scripts for adding twc files under files tab.?Created user event for updating the company tl id and making fields inline.
1534747 | 2026-05-14 | Giuseppe Dev | SRDevNS | 3.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-29 | feedback list github oprations
1533645 | 2026-05-14 | Javeed Shabeer | SRDevOSSMSpace | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-15 | - Worked on Towercom Issue tickets.
1533589 | 2026-05-14 | Jesna John | SRDevOSSMSpace | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-15 | Worked on issue tickets. Worked on Towercom to-dos for dispalying table for uploaded images, adding separate sections for open images uploaded in trouble tickets.?Created user event scripts for adding twc files under files tab.?Created user event for updating the company tl id and making fields inline.
1533613 | 2026-05-14 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-05-15 | Working through issues list and resolving
1534746 | 2026-05-13 | Giuseppe Dev | SRDevNS | 5.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-29 | feedback list
1533588 | 2026-05-13 | Jesna John | SRDevOSSMSpace | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-15 | Worked on issue tickets. Worked on Towercom to-dos for dispalying table for uploaded images, adding separate sections for open images uploaded in trouble tickets.?Created user event scripts for adding twc files under files tab.?Created user event for updating the company tl id and making fields inline.
1533587 | 2026-05-12 | Jesna John | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-15 | Worked on issue tickets. Worked on Towercom to-dos for dispalying table for uploaded images, adding separate sections for open images uploaded in trouble tickets.?Created user event scripts for adding twc files under files tab.?Created user event for updating the company tl id and making fields inline.
1533644 | 2026-05-12 | Javeed Shabeer | SRDevOSSMSpace | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-15 | - Worked on Towercom Issue tickets.
1533643 | 2026-05-11 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-15 | - Worked on Towercom Issue tickets.
1533443 | 2026-05-08 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-05-11 | Import Items, New Vendors, Vendor Bank Details, Opening Balances in Sandbox
1533153 | 2026-05-08 | Jesna John | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-08 | Worked on the SAF page issue mentioned by customer.
1533205 | 2026-05-08 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-08 | - Worked on creating the Equipment Action Record using NetSuite’s standard module ‘N/record’, as the framework approach was causing errors.
1533187 | 2026-05-08 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-05-08 | Working through issues list, call with Mark and Amy closing issues and showing how to work system
1533186 | 2026-05-07 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-05-08 | Working through issues list, call with Mark and Amy closing issues and showing how to work system
1533203 | 2026-05-07 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-08 | - Worked on creating the Equipment Action Record using NetSuite’s standard module ‘N/record’, as the framework approach was causing errors.
1533442 | 2026-05-06 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-05-11 | Import Items, New Vendors, Vendor Bank Details, Opening Balances in Sandbox
1534732 | 2026-05-05 | Giuseppe Dev | SRDevNS | 0.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-29 | feedback list
1533202 | 2026-05-04 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-08 | - Worked on creating the Equipment Action Record using NetSuite’s standard module ‘N/record’, as the framework approach was causing errors.
1534731 | 2026-05-01 | Giuseppe Dev | SRDevNS | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-29 | SAF :: Finalize feedback list
1532847 | 2026-05-01 | Carlos Gamiz | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-01 | meetings, dev meetings , go through changes with dev
1532759 | 2026-04-30 | Giuseppe Dev | SRDevNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-01 | preparing for session SAF session
1532638 | 2026-04-30 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-30 | - Worked on a ticket to auto populate the Accreditation Status to "SP Expired" based on Safe Pass Status is set to "Expired" on Profile Record.?- Working on the task assigned by Giuseppe to create the Equip Action record. (Getting an error while saving the record, (Maximum call stack size exceeded) need to resolve it.
1532623 | 2026-04-30 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-04-30 | Working through issues list ?reviewing schemas and working on tables
1532576 | 2026-04-30 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-04-30 | Meeting with Mark on Projects?Meeting with Grainne and Stephanie on Finance?Items import to SB
1532575 | 2026-04-29 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-04-30 | Meeting with Mark on Projects?Meeting with Grainne and Stephanie on Finance?Items import to SB
1532637 | 2026-04-29 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-30 | - Worked on a ticket to auto populate the Accreditation Status to "SP Expired" based on Safe Pass Status is set to "Expired" on Profile Record.?- Working on the task assigned by Giuseppe to create the Equip Action record. (Getting an error while saving the record, (Maximum call stack size exceeded) need to resolve it.
1532609 | 2026-04-29 | Jesna John | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-30 | Worked in trouble tickets page for adding add panel to upload photos and resolution image for new tickets being created. Restricting resolve of tickets if no resolution image added.
1532622 | 2026-04-29 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-04-30 | Working through issues list ?reviewing schemas and working on tables
1532758 | 2026-04-28 | Giuseppe Dev | SRDevNS | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-01 | SRF :: Eq. Libraray Implementation
1532608 | 2026-04-28 | Jesna John | SRDevOSSMSpace | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-30 | Worked in trouble tickets page for adding add panel to upload photos and resolution image for new tickets being created. Restricting resolve of tickets if no resolution image added.
1532621 | 2026-04-28 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-04-30 | Working through issues list ?reviewing schemas and working on tables
1532574 | 2026-04-28 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-04-30 | Meeting with Mark on Projects?Meeting with Grainne and Stephanie on Finance?Items import to SB
1532757 | 2026-04-27 | Giuseppe Dev | SRDevNS | 5.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-01 | feedback list SRF :: Eq. Libraray Implementation
1532607 | 2026-04-27 | Jesna John | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-30 | Worked in trouble tickets page for adding add panel to upload photos and resolution image for new tickets being created. Restricting resolve of tickets if no resolution image added.
1532636 | 2026-04-27 | Javeed Shabeer | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-30 | - Worked on a ticket to auto populate the Accreditation Status to "SP Expired" based on Safe Pass Status is set to "Expired" on Profile Record.?- Working on the task assigned by Giuseppe to create the Equip Action record. (Getting an error while saving the record, (Maximum call stack size exceeded) need to resolve it.
1532846 | 2026-04-27 | Carlos Gamiz | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-05-01 | meetings, dev meetings , go through changes with dev
1532573 | 2026-04-27 | Dave O'Hanlon | SRConNS | 1.25 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-04-30 | Meeting with Mark on Projects?Meeting with Grainne and Stephanie on Finance?Items import to SB
1532289 | 2026-04-24 | Giuseppe Dev | SRDevNS | 6.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | feedback list weekly review
1532135 | 2026-04-24 | Jesna John | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-24 | Working on trouble ticket page for editing resolution images, hiding resolution files section, resolve restriction.
1532288 | 2026-04-23 | Giuseppe Dev | SRDevNS | 4.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | feedback list project meeting with client
1532134 | 2026-04-23 | Jesna John | SRDevOSSMSpace | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-24 | Working on trouble ticket page for editing resolution images, hiding resolution files section, resolve restriction.
1532133 | 2026-04-22 | Jesna John | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-24 | Working on trouble ticket page for editing resolution images, hiding resolution files section, resolve restriction.
1532287 | 2026-04-20 | Giuseppe Dev | SRDevNS | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | nexus records implementation
1532266 | 2026-04-17 | Giuseppe Dev | SRDevNS | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | srf call with Sean/Carlos
1531790 | 2026-04-17 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-20 | - Worked on the Towercom issue ticket: implemented conditional UI behavior for infrastructure records.
1531743 | 2026-04-17 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-04-17 | Nexus testing and working through logged issues
1531645 | 2026-04-17 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-04-17 | Towercom meeting with Mark re Projects?Custom Fields and Forms Work - Projects
1532265 | 2026-04-16 | Giuseppe Dev | SRDevNS | 2.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | feedback list
1531742 | 2026-04-16 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-04-17 | Nexus testing and working through logged issues
1531425 | 2026-04-15 | Jesna John | SRDevOSSMSpace | 6 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-15 | Worked in Trouble tickets pages for adding comments for Resolve and cancel tickets, setting assigned to fields, delete files and save action updates.
1531696 | 2026-04-15 | Carlos Gamiz | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-17 | meetings and manage team
1532264 | 2026-04-14 | Giuseppe Dev | SRDevNS | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | feedback list review feedback items
1531424 | 2026-04-14 | Jesna John | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-15 | Worked in Trouble tickets pages for adding comments for Resolve and cancel tickets, setting assigned to fields, delete files and save action updates.
1531644 | 2026-04-14 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-04-17 | Towercom meeting with Mark re Projects?Custom Fields and Forms Work - Projects
1532263 | 2026-04-13 | Giuseppe Dev | SRDevNS | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | feedback list
1531423 | 2026-04-13 | Jesna John | SRDevOSSMSpace | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-15 | Worked in Trouble tickets pages for adding comments for Resolve and cancel tickets, setting assigned to fields, delete files and save action updates.
1531741 | 2026-04-13 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-04-17 | Nexus testing and working through logged issues
1531250 | 2026-04-10 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-04-10 | Working through issues list and resolving
1531193 | 2026-04-10 | Jesna John | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | Worked in trouble ticket page - Resolve tickets, Cancel tickets, Create new tickets, Upload resolution files to the trouble ticket, display of resolution files in trouble tickets page. Edit and save of tickets.
1532238 | 2026-04-09 | Giuseppe Dev | SRDevNS | 2.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | feedback list issue list review
1531236 | 2026-04-09 | Javeed Shabeer | SRDevOSSMSpace | 5.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | - Worked on Towercom New page to view the additional details such as TME, ATEM, GIE?- Worked on Towercom Issue Tickets
1531192 | 2026-04-09 | Jesna John | SRDevOSSMSpace | 6 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | Worked in trouble ticket page - Resolve tickets, Cancel tickets, Create new tickets, Upload resolution files to the trouble ticket, display of resolution files in trouble tickets page. Edit and save of tickets.
1532239 | 2026-04-08 | Giuseppe Dev | SRDevNS | 2.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | javeed review
1531235 | 2026-04-08 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | - Worked on Towercom New page to view the additional details such as TME, ATEM, GIE?- Worked on Towercom Issue Tickets
1531207 | 2026-04-08 | Carlos Gamiz | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | documentation , meetings
1531191 | 2026-04-07 | Jesna John | SRDevOSSMSpace | 7 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | Worked in trouble ticket page - Resolve tickets, Cancel tickets, Create new tickets, Upload resolution files to the trouble ticket, display of resolution files in trouble tickets page. Edit and save of tickets.
1531234 | 2026-04-07 | Javeed Shabeer | SRDevOSSMSpace | 6 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | - Worked on Towercom New page to view the additional details such as TME, ATEM, GIE?- Worked on Towercom Issue Tickets
1531190 | 2026-04-06 | Jesna John | SRDevOSSMSpace | 6.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | Worked in trouble ticket page - Resolve tickets, Cancel tickets, Create new tickets, Upload resolution files to the trouble ticket, display of resolution files in trouble tickets page. Edit and save of tickets.
1531233 | 2026-04-06 | Javeed Shabeer | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-10 | - Worked on Towercom New page to view the additional details such as TME, ATEM, GIE?- Worked on Towercom Issue Tickets
1532219 | 2026-04-02 | Giuseppe Dev | SRDevNS | 2.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | trouble tickets review
1531115 | 2026-04-02 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-08 | - Worked on updating the Towercom inventory page for adding tables.
1531018 | 2026-04-02 | Jesna John | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-02 | Working on Trouble tickets page.
1531006 | 2026-04-02 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-04-02 | Towercom Finance planning session
1532218 | 2026-04-01 | Giuseppe Dev | SRDevNS | 1.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-27 | srf project plan meeting
1531114 | 2026-04-01 | Javeed Shabeer | SRDevOSSMSpace | 2.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-08 | - Worked on updating the Towercom inventory page for adding tables.
1531017 | 2026-04-01 | Jesna John | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-04-02 | Working on Trouble tickets page.
1530682 | 2026-03-31 | Jesna John | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-31 | Working on Trouble tickets page.
1530685 | 2026-03-31 | Javeed Shabeer | SRDevOSSMSpace | 5.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-31 | - Working on Creating the Inventory page for towercom.
1530681 | 2026-03-30 | Jesna John | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-31 | Working on Trouble tickets page.
1530341 | 2026-03-27 | Giuseppe Dev | SRDevNS | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | instructing Jesna/Javeed on what to do meeting about SAF/SRF and troubled tickets
1530169 | 2026-03-27 | Jesna John | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-27 | work on tickets
1530108 | 2026-03-27 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-03-27 | Projects Testing?Custom fields for Projects?Custom Project Form?Project Templates?Elimination Sub setup and testing
1530340 | 2026-03-26 | Giuseppe Dev | SRDevNS | 0.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | prep session for developers
1530187 | 2026-03-26 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : UAT Testing (Project Task) | Yes | 2026-03-27 | Testing of Nexus and setting up of users for Towercom and profiles and walkthrough of process
1530338 | 2026-03-25 | Giuseppe Dev | SRDevNS | 2.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | Accreditation catch up meeting with Carlos and Sean
1530339 | 2026-03-24 | Giuseppe Dev | SRDevNS | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | session with Sean
1530164 | 2026-03-24 | Carlos Gamiz | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-27 | meetings, manage dev, assign tasks to dev
1530337 | 2026-03-23 | Giuseppe Dev | SRDevNS | 1.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | Accreditation :: cert statuses maintenance
1530107 | 2026-03-23 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Form Design and Custom Fields (Project Task) | Yes | 2026-03-27 | Projects Testing?Custom fields for Projects?Custom Project Form?Project Templates?Elimination Sub setup and testing
1530318 | 2026-03-21 | Giuseppe Dev | SRDevNS | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | Company Profile (Cert Management)
1530317 | 2026-03-20 | Giuseppe Dev | SRDevNS | 10.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | SAF, Accreditation & Company Profile :: final tweaks SAF :: prep for meeting catch up meeting call with Carlos and Anna
1529690 | 2026-03-20 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-03-23 | updating tables with missing custom records and updating list options from updated schemas
1530316 | 2026-03-19 | Giuseppe Dev | SRDevNS | 6 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | Accreditation & Company Profile SAF :: meeting
1530315 | 2026-03-18 | Giuseppe Dev | SRDevNS | 5.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | SAF :: work in progress SAF :: testing and fine tuning
1529689 | 2026-03-18 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-03-23 | updating tables with missing custom records and updating list options from updated schemas
1529613 | 2026-03-18 | Sean Munroe | SRConNS | 6 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-03-20 | Updating Tables with missing custom records, and updating lists for options from updated schemas
1530314 | 2026-03-17 | Giuseppe Dev | SRDevNS | 3.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | SAF :: work in progress
1530389 | 2026-03-15 | Giuseppe Dev | SRDevNS | 0 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | SAF :: work in progress
1530303 | 2026-03-14 | Giuseppe Dev | SRDevNS | 6.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | SAF :: work in progress
1530302 | 2026-03-13 | Giuseppe Dev | SRDevNS | 5.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | SAF :: work in progress review next steps
1529219 | 2026-03-13 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Radix System Replacement Testing (Project Task) | Yes | 2026-03-13 | Projects Structures and Fixed Assets calls
1530301 | 2026-03-12 | Giuseppe Dev | SRDevNS | 7 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | SAF :: work in progress
1529292 | 2026-03-12 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-03-13 | Modifying custom records reviewing changes to schema and re importing data against changes in record types
1529218 | 2026-03-12 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Radix System Replacement Testing (Project Task) | Yes | 2026-03-13 | Projects Structures and Fixed Assets calls
1530300 | 2026-03-11 | Giuseppe Dev | SRDevNS | 2.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | ACA Review internal call with Sean/Anna/Carlos
1529291 | 2026-03-11 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-03-13 | Modifying custom records reviewing changes to schema and re importing data against changes in record types
1529217 | 2026-03-10 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Radix System Replacement Testing (Project Task) | Yes | 2026-03-13 | Projects Structures and Fixed Assets calls
1530299 | 2026-03-09 | Giuseppe Dev | SRDevNS | 3.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-30 | SAF :: work in progress meeting about projects implementation
1529226 | 2026-03-09 | Jesna John | SRDevOSSMSpace | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-13 | Worked on the site access page to populate fields on the access page from the radix system.
1528757 | 2026-03-08 | Giuseppe Dev | SRDevNS | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-09 | SAF :: work in progress
1528756 | 2026-03-07 | Giuseppe Dev | SRDevNS | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-09 | SAF :: Calendar Control SAF :: getting started review next steps
1528684 | 2026-03-06 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Fixed Assets (Project Task) | Yes | 2026-03-06 | Towercom Finance activities planning session?Fixed Assets testing
1528650 | 2026-03-06 | Jesna John | SRDevOSSMSpace | 6 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-06 | Worked on site info page updates - added fields and sections for site info page.?Worked on the site access locator panel, added filters and tables based on the radix system.?Worked on the SRF page for adding the filters in the locator panel and on the site access details page to populate fields and tables.
1528755 | 2026-03-05 | Giuseppe Dev | SRDevNS | 7.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-09 | porting KTL APEX app review meeting
1528649 | 2026-03-05 | Jesna John | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-06 | Worked on site info page updates - added fields and sections for site info page.?Worked on the site access locator panel, added filters and tables based on the radix system.?Worked on the SRF page for adding the filters in the locator panel and on the site access details page to populate fields and tables.
1528661 | 2026-03-05 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-06 | - Attended Towercom Dev meeting?- Worked on Towercom features:? - Space Request: ? Add submit button if status is 'Draft' or 'FeedbackIssued'? NOTE: if status is FeedbackIssued then set to 'Resubmitted'? if status not 'Draft' or 'FeedbackIssued' then the user should no longer be able to edit the request
1528683 | 2026-03-05 | Dave O'Hanlon | SRConNS | 3 | Approved | Consultancy : Fixed Assets (Project Task) | Yes | 2026-03-06 | Towercom Finance activities planning session?Fixed Assets testing
1528754 | 2026-03-04 | Giuseppe Dev | SRDevNS | 1.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-09 | porting KTL APEX app
1528648 | 2026-03-04 | Jesna John | SRDevOSSMSpace | 6 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-06 | Worked on site info page updates - added fields and sections for site info page.?Worked on the site access locator panel, added filters and tables based on the radix system.?Worked on the SRF page for adding the filters in the locator panel and on the site access details page to populate fields and tables.
1528753 | 2026-03-03 | Giuseppe Dev | SRDevNS | 0.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-09 | porting KTL APEX app
1528647 | 2026-03-03 | Jesna John | SRDevOSSMSpace | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-06 | Worked on site info page updates - added fields and sections for site info page.?Worked on the site access locator panel, added filters and tables based on the radix system.?Worked on the SRF page for adding the filters in the locator panel and on the site access details page to populate fields and tables.
1528655 | 2026-03-03 | Carlos Gamiz | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-06 | meetings, data changes
1528660 | 2026-03-02 | Javeed Shabeer | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-06 | - Attended Towercom Dev meeting?- Worked on Towercom features:? - Space Request: ? Add submit button if status is 'Draft' or 'FeedbackIssued'? NOTE: if status is FeedbackIssued then set to 'Resubmitted'? if status not 'Draft' or 'FeedbackIssued' then the user should no longer be able to edit the request
1528646 | 2026-03-02 | Jesna John | SRDevOSSMSpace | 5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-06 | Worked on site info page updates - added fields and sections for site info page.?Worked on the site access locator panel, added filters and tables based on the radix system.?Worked on the SRF page for adding the filters in the locator panel and on the site access details page to populate fields and tables.
1528252 | 2026-02-27 | Giuseppe Dev | SRDevNS | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-02 | file cabinet meeeting catch-up meeting
1528129 | 2026-02-27 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-02-27 | Finance Go-Live checklist created and sent
1528251 | 2026-02-26 | Giuseppe Dev | SRDevNS | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-02 | session XXIII
1528128 | 2026-02-26 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Roles and Permissions (Project Task) | Yes | 2026-02-27 | Finance Go-Live checklist created and sent
1528250 | 2026-02-25 | Giuseppe Dev | SRDevNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-02 | session XXII
1528249 | 2026-02-24 | Giuseppe Dev | SRDevNS | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-02 | session XXI
1528248 | 2026-02-23 | Giuseppe Dev | SRDevNS | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-03-02 | session XX
1527418 | 2026-02-20 | Giuseppe Dev | SRDevNS | 4.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-23 | session XIX
1527306 | 2026-02-20 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-02-20 | Initial Fixed Asset setup work in Sandbox?Towercom Onsite Finance Session ?Finance Project Plan
1527417 | 2026-02-19 | Giuseppe Dev | SRDevNS | 3.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-23 | session XVIII project meetings
1527305 | 2026-02-19 | Dave O'Hanlon | SRConNS | 6 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-02-20 | Initial Fixed Asset setup work in Sandbox?Towercom Onsite Finance Session ?Finance Project Plan
1527304 | 2026-02-18 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-02-20 | Initial Fixed Asset setup work in Sandbox?Towercom Onsite Finance Session ?Finance Project Plan
1527416 | 2026-02-17 | Giuseppe Dev | SRDevNS | 2.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-23 | session XVII call with Anna
1527303 | 2026-02-16 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : System Training (Project Task) | Yes | 2026-02-20 | Initial Fixed Asset setup work in Sandbox?Towercom Onsite Finance Session ?Finance Project Plan
1526878 | 2026-02-13 | Giuseppe Dev | SRDevNS | 4.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-16 | session XVI code / comments clean-up
1526696 | 2026-02-13 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-02-13 | Meeting with Grainne re Items and tax codes?Class and Item dependencies Import/Setup in SB
1526791 | 2026-02-13 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-02-13 | Radix tables imports and config
1526877 | 2026-02-12 | Giuseppe Dev | SRDevNS | 2.25 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-16 | session XV
1526876 | 2026-02-11 | Giuseppe Dev | SRDevNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-16 | session XIV
1526624 | 2026-02-11 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-02-11 | Meeting with Grainne re Items and tax codes?Class and Item dependencies Import/Setup in SB
1526875 | 2026-02-10 | Giuseppe Dev | SRDevNS | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-16 | session XIII fixing site duplications
1526790 | 2026-02-09 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-02-13 | Radix tables imports and config
1526350 | 2026-02-06 | Giuseppe Dev | SRDevNS | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-09 | session XII
1526349 | 2026-02-05 | Giuseppe Dev | SRDevNS | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-09 | session XI
1526253 | 2026-02-05 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-02-06 | Towercom Finance?Session with Grainne re Items?System setup
1526348 | 2026-02-04 | Giuseppe Dev | SRDevNS | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-09 | session X
1526252 | 2026-02-04 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-02-06 | Towercom Finance?Session with Grainne re Items?System setup
1525909 | 2026-01-30 | Giuseppe Dev | SRDevNS | 2.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-03 | Session IX
1525605 | 2026-01-30 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Fixed Assets (Project Task) | Yes | 2026-01-30 | Towercom Finance Requirements?Setup FAM in Sandbox?Setup and testing Adjustment Period
1525908 | 2026-01-29 | Giuseppe Dev | SRDevNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-03 | session VIII
1525907 | 2026-01-28 | Giuseppe Dev | SRDevNS | 3.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-03 | session VII call with Mark
1525520 | 2026-01-28 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Fixed Assets (Project Task) | Yes | 2026-01-28 | Towercom Finance Requirements?Setup FAM in Sandbox?Setup and testing Adjustment Period
1525906 | 2026-01-27 | Giuseppe Dev | SRDevNS | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-02-03 | session VI
1525695 | 2026-01-27 | Carlos Gamiz | SRConNS | 4 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-01-30 | meetings for data structure
1525007 | 2026-01-23 | Giuseppe Dev | SRDevNS | 3 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-01-26 | session V site locator :: search by location fine tuning
1525006 | 2026-01-22 | Giuseppe Dev | SRDevNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-01-26 | session IV
1524864 | 2026-01-22 | Dave O'Hanlon | SRConNS | 6 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-01-23 | Towercom Onsite Workshop: Billing
1525005 | 2026-01-21 | Giuseppe Dev | SRDevNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-01-26 | session III
1525004 | 2026-01-20 | Giuseppe Dev | SRDevNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-01-26 | session II
1525003 | 2026-01-19 | Giuseppe Dev | SRDevNS | 3.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-01-26 | session I
1524407 | 2026-01-14 | Javeed Shabeer | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-01-16 | - Worked on changes requested by Sean on the Custom Records.
1525882 | 2026-01-13 | Anna Carolan | SRConPMNS | 1 | Approved | Project Management (Project Task) | No | 2026-02-02 | Meeting with dev on plan
1524406 | 2026-01-13 | Javeed Shabeer | SRDevOSSMSpace | 2 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-01-16 | - Worked on changes requested by Sean on the Custom Records.
1525060 | 2026-01-13 | Giuseppe Dev | SRDevOSSMSpace | 0.75 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2026-01-26 | meeting with Carlos & Anna
1523907 | 2026-01-09 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Custom Records (Project Task) | Yes | 2026-01-09 | Working through Custom Records for tables for Radix
1523732 | 2026-01-08 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-01-08 | Towercom SRF Workshop?Items Set up meeting with Grainne
1523731 | 2026-01-07 | Dave O'Hanlon | SRConNS | 6 | Approved | Consultancy : Opening Balances and Co live (Project Task) | Yes | 2026-01-08 | Towercom SRF Workshop?Items Set up meeting with Grainne
1523328 | 2026-01-02 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2026-01-02 | Item strategy and email to Towercom
1523037 | 2025-12-23 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-12-23 | Radix Custom records and working through Sample Data
1522900 | 2025-12-19 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-12-19 | Creation of Radix menu in Netsuite ?Reviewing data structure from radix sent by mark?updating custom records in Netsuite
1522899 | 2025-12-18 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-12-19 | Creation of Radix menu in Netsuite ?Reviewing data structure from radix sent by mark?updating custom records in Netsuite
1522898 | 2025-12-17 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-12-19 | Creation of Radix menu in Netsuite ?Reviewing data structure from radix sent by mark?updating custom records in Netsuite
1522811 | 2025-12-17 | Javeed Shabeer | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2025-12-19 | Worked on creating Custom Records based on the detailed requirements provided by Sean.
1522763 | 2025-12-17 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-12-19 | Onsite Finance Day
1522897 | 2025-12-16 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-12-19 | Creation of Radix menu in Netsuite ?Reviewing data structure from radix sent by mark?updating custom records in Netsuite
1522810 | 2025-12-16 | Javeed Shabeer | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2025-12-19 | Worked on creating Custom Records based on the detailed requirements provided by Sean.
1522809 | 2025-12-15 | Javeed Shabeer | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2025-12-19 | Worked on creating Custom Records based on the detailed requirements provided by Sean.
1522353 | 2025-12-12 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-12-12 | Testing of Customer and Vendor Portal ?Call on Radix Db ?And going through Tables with Dev
1522352 | 2025-12-08 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-12-12 | Testing of Customer and Vendor Portal ?Call on Radix Db ?And going through Tables with Dev
1521770 | 2025-12-04 | Sean Munroe | SRConNS | 0 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | No | 2025-12-05 | Onsite workshop on SAF
1522336 | 2025-12-04 | Giuseppe Dev | SRDevOSSMSpace | 1.5 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2025-12-12 | ctach-up meeting
1521843 | 2025-12-04 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-12-08 | Towercom Onsite: Radix tables to be replicated, Equipment Workshop, SAF Workshop
1521769 | 2025-12-03 | Sean Munroe | SRConNS | 8 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-12-05 | Onsite workshop on SAF
1521842 | 2025-12-03 | Dave O'Hanlon | SRConNS | 6 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-12-08 | Towercom Onsite: Radix tables to be replicated, Equipment Workshop, SAF Workshop
1521207 | 2025-11-24 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-11-28 | Meeting to discuss Accreditations and information needed from Radix and input as custom records in netsuite
1521148 | 2025-11-24 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : System Training (Project Task) | Yes | 2025-11-28 | Meeting with Mark and Amy to show NetSuite standard CRM and discuss Company Profiles
1520596 | 2025-11-21 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-11-21 | Towercom finance requirements review
1520595 | 2025-11-20 | Dave O'Hanlon | SRConNS | 1 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-11-21 | Towercom finance requirements review
1520631 | 2025-11-20 | Javeed Shabeer | SRDevOSSMSpace | 4 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2025-11-21 | - Worked on the Towercom client to create multiple custom records (OSSM072 - Agent Passes Options, OSSM072 - Company, OSSM072 - Company Accreditation Status, OSSM072 - Company Available Type, OSSM072 - Company Classification, OSSM072 - Company Primary Contact, OSSM072 - Company Type, OSSM072 - No/Active Options, OSSM072 - Profile, OSSM072 - Profile Accreditation Status, OSSM072 - Track Key, OSSM072 - Yes/No Options).?- Also supported Sean with mapping data types from NetSuite to MySQL.
1520917 | 2025-11-20 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-11-24 | extracting Radix data and getting into a format for mark and generation of custom records and fields with Dev
1520916 | 2025-11-19 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-11-24 | extracting Radix data and getting into a format for mark and generation of custom records and fields with Dev
1520915 | 2025-11-18 | Sean Munroe | SRConNS | 1 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-11-24 | extracting Radix data and getting into a format for mark and generation of custom records and fields with Dev
1520630 | 2025-11-18 | Javeed Shabeer | SRDevOSSMSpace | 8 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2025-11-21 | - Worked on the Towercom client to create multiple custom records (OSSM072 - Agent Passes Options, OSSM072 - Company, OSSM072 - Company Accreditation Status, OSSM072 - Company Available Type, OSSM072 - Company Classification, OSSM072 - Company Primary Contact, OSSM072 - Company Type, OSSM072 - No/Active Options, OSSM072 - Profile, OSSM072 - Profile Accreditation Status, OSSM072 - Track Key, OSSM072 - Yes/No Options).?- Also supported Sean with mapping data types from NetSuite to MySQL.
1519253 | 2025-11-06 | Sean Munroe | SRConNS | 8 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-11-07 | Meeting with Towercom onsite to go through requirements and solutions
1519608 | 2025-11-06 | Giuseppe Dev | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2025-11-10 | towercom :: project manager demo prep
1519157 | 2025-11-06 | Dave O'Hanlon | SRConPMNS | 4 | Approved | Project Management (Project Task) | No | 2025-11-07 | Towercom Onsite session 06/11
1520830 | 2025-11-06 | Anna Carolan | SRConPMNS | 8 | Approved | Project Management (Project Task) | No | 2025-11-24 | Planning and Accreditation workshop
1519254 | 2025-11-05 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-11-07 | Extracting Tables from Radix into Mysql
1519607 | 2025-11-03 | Giuseppe Dev | SRDevOSSMSpace | 1 | Approved | Development : Radix System Replacement - Phase 1 (Project Task) | No | 2025-11-10 | mysql :: restore dump & analyse data
1518801 | 2025-10-29 | Sean Munroe | SRConNS | 3 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-11-01 | Finalise Vendor Imports and Setup of Projects and reviewing radix tables
1518800 | 2025-10-28 | Sean Munroe | SRConNS | 5 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-11-01 | Finalise Vendor Imports and Setup of Projects and reviewing radix tables
1518370 | 2025-10-24 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-10-28 | Import of Vendors and config of sb and extraction of data from radix sql backup
1518369 | 2025-10-20 | Sean Munroe | SRConNS | 4 | Approved | Consultancy : Sandbox Configuration (Project Task) | Yes | 2025-10-28 | Import of Vendors and config of sb and extraction of data from radix sql backup
1517608 | 2025-10-17 | Sean Munroe | SRConNS | 6 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2025-10-17 | Getting radix backup files to extract tables and setting up mysql?Import of Employee Records ?Import of Customers and Contacts
1517607 | 2025-10-16 | Sean Munroe | SRConNS | 6 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2025-10-17 | Getting radix backup files to extract tables and setting up mysql?Import of Employee Records ?Import of Customers and Contacts
1517606 | 2025-10-13 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2025-10-17 | Getting radix backup files to extract tables and setting up mysql?Import of Employee Records ?Import of Customers and Contacts
1517208 | 2025-10-10 | Sean Munroe | SRConNS | 8 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2025-10-10 | Sandbox setup and COA imports and setup
1517207 | 2025-10-09 | Sean Munroe | SRConNS | 6 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2025-10-10 | Sandbox setup and COA imports and setup
1517623 | 2025-10-09 | Anna Carolan | SRConPMNS | 2 | Approved | Project Management (Project Task) | No | 2025-10-17 | PM
1517206 | 2025-10-08 | Sean Munroe | SRConNS | 2 | Approved | Consultancy : Configuration of Production (Project Task) | Yes | 2025-10-10 | Sandbox setup and COA imports and setup
1516837 | 2025-10-02 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-10-03 | Bundle Deployment?Set up Subsidiaries?Sandbox refresh?Project KO meeting
1516836 | 2025-10-01 | Dave O'Hanlon | SRConNS | 2 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-10-03 | Bundle Deployment?Set up Subsidiaries?Sandbox refresh?Project KO meeting
1516618 | 2025-09-29 | Dave O'Hanlon | SRConNS | 4 | Approved | Consultancy : ERP Consultancy and Configuration (Project Task) | Yes | 2025-10-01 | Account Bundle Deployment
| Overall Total |  |  | 1,392.0 | [5 empty] | 0

## Sheet1
Employee |  | Time
Dave O'Hanlon | Implementation | 250 | 17.96%
Giuseppe Dev | Development | 400 | 28.74%
Ladislav Zimanyi | Management | 24.5 | 1.76%
Sean Munroe | Implementation | 284 | 20.4%
Javeed Shabeer | Development | 168 | 12.07%
Jesna John | Development | 170.5 | 12.25%
Anna Carolan | Management | 43 | 3.089%
Abin Pious | Development | 16 | 1.149%
Carlos Gamiz | Management | 36 | 2.586%
1392
Area |  | Time
Implementation |  | 534 | 38.36%
Development |  | 754.5 | 54.2%
Management |  | 103.5 | 7.435%
1392