## Tracker
Original | FP Programme Tracker | [159 empty] | Design & Construction Programme Tracker 'OCELOT'
Index | Site Details | [17 empty] | Full Planning | [74 empty] | Planning Compliance | [44 empty] | Customer Demand | [21 empty] | Gating |  |  |  |  | Structure | [5 empty] | Power Solution | [11 empty] | Design | [32 empty] | PCM | [8 empty] | Notifications | [12 empty] | Construction | [20 empty] | Post RFI Works | [5 empty] | Acceptance | [5 empty] | Handover | [5 empty] | HT |  | Finance
Milestone | [20 empty] | MS | [21 empty] | MS | [11 empty] | MS |  |  |  | MS | [8 empty] | MS |  |  |  | MS | [89 empty] | MS |  | *NOT Updated - TBC If Required | [36 empty] | MS | MS |  |  | MS | MS |  | MS |  |  |  |  | MS |  | MS | [22 empty] | N.B. Same Date as FP Compliance | [18 empty] | MS |  | MS | [18 empty] | Commerical Governance
Responsible | AP | AP | AP | AP | AP | KMcH | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | TS |  | LOC | LOC | RR |  | RR | SB | LOC | LOC | LOC | LOC | SB | LOC | RR | RR | LOC | LOC | LOC | LOC | LOC | RR | *NOT Updated - NOT Required | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC |  | LOC | LOC | LOC |  | LOC | LOC | LOC | LOC | LOC | LOC | LOC |  | LOC | LOC | LOC |  | LOC | LOC | LOC | RR | LOC | RR | RR | RR | RR | RR | AP | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | RR | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC | LOC |  | AP | RH | RH | RH | RH | RH | RH | RH | RH | RH | RH | RH | RH | RH | RH | RH | RH |  | AP | AP |  | SA | SA | SA | SA | SA | SA | SB |  | SB | SB | SB | SB | SB | TG | TG | TG | TG | TG | TG | TG | TG | TG | TG | TG | SB | SB | SB | SB | SB | SB | TS | TS | BAP | TG | TS | TS | TS | TS | BAP | TG | TS |  | TS | SB | SB |  | SB |  | SB | SB | SB | SB | SB |  | SB | SB | SB | SB | SB | SB | SB | TS | SB | SB | BAP | BAP |  | TG |  | RH | RH | RH | RH | RH | TG | BAP/COB | BAP/COB | BAP/COB |  |  |  | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS |  |  | SA | TS | TS | TS | TS | TS | TS |  |  | TS |  |  | SB | SB | SB | SB | SB | SB | SB |  |  | Finance | [11 empty] | Financial Analysis
| Site ID | Site Name | County | Portfolio | UniqueID | Budget Open/ Closed | Easting | Northing | Latitude | Longitude | Current Structure Type | Current Height (m) | Proposed Structure Type | Proposed Height (m) | Actual Structure Type | Actual Height (m) | Structure Location | Notes 05/06 | LPA | Planning Review Category | FP Instructed Forecasted | FP Instructed Actual | Planner | FP Drawing Provider | Map Scale | FP Drawing Instructed | FP Drawing Issued | FP Drawing Revision Required | FP Drawing Revision Counter | FP Drawing Approved | LOC Requested | LOC Received | Photomontage Required | Photomontage Requirement | Photomontage Instructed | Photomontage Completed | Heritage Report Required | Applicant | RAG Decision Forecast | FI Forecast | Appeal Forecast | Planning Application Submitted Forecast | Planning Application Submitted Actual | Planning Application Received by LPA | Application Reference | Application Invalidated | Invalidation Reason | FI Request | FI Request Deadline | FI Submission Date | Clarification of FI Request | Clarification of FI Request Deadline | Clarification of FI Submission Date | LPA Initial Decision Date Forecast | LPA Initial Decision Date Actual | LPA Initial Decision Status | No of 3rd party Submissions / Objections | LPA Final Decision Date Forecast | LPA Final Decision Date Actual | LPA Final Decision Status | Planning Decision Year | ABP Appeal Deadline | 1st Party Appeal Submitted | 3rd Party Appeal Submitted | ABP Reference | Forecast ABP Final Decision Date | Forecast ABP Final Decision | Actual ABP Final Decision Date | Actual ABP Decision | Forecast FP Final Decision Date | Forecast FP Final Decision | Actual FP Final Decision Date | Actual FP Final Decision | FP Expiry Date | FP Status | TL Schedule / Part | True Part B | FP HOP Completed | Radix FP Fields Updated | Applicaton Status | Application Status - DO NOT CHANGE | eir Constraints List(s) | eir List Issued November 2020 | eir List Issued June 2021 | eir 'Red' List September 2021 | LPA Submission Deadline | Equiendo Review | Review Date | Option A or B | 3rd party Submissions / Objections by Competitors | 3rd Party Appeal Submitted by Competitors | Radix Height Updates | Notes | Planning Conditions to be Discharged | Financial Contribution / Bond Required | AWL Required | Colour Scheme Required | Landscaping Plan / Scheme Required | Traffic / Pedestrian Management Plan Required | Construction Management/ Safety Plan Required | Waste Management Plan Required | Site Reinstatement / Exisitng Equipment Removal Plan Required | Archaeological Monitoring Plan Required | Working Days / Hours Confirmation Required | Surface Water Drainage Plan Required | Noise / Accoustics Mitigation Plan Required | Commencement Notice Required | Other Item(s) Required | Financial Contribution / Bond Sent to LPA | Financial Contribution / Bond Accepted by LPA | IAA AWL Mail Sent | IAA AWL Response Received | Colour Scheme Sent to LPA | Colour Scheme Accepted by LPA | Landscaping Plan Sent to LPA | Landscaping Plan Accepted by LPA | Traffic / Pedestrian Management Plan Sent to LPA | Traffic / Pedestrian Management Plan Accepted by LPA | Construction Management/ Safety Plan Sent to LPA | Construction Management/ Safety Plan Accepted by LPA | Waste Management Plan Sent to LPA | Waste Management Plan Accepted by LPA | Site Reinstatement / Exisitng Equipment Removal Plan Sent to LPA | Site Reinstatement / Exisitng Equipment Removal Plan Accepted by LPA | Archaeological Monitoring Plan Sent to LPA | Archaeological Monitoring Plan Accepted by LPA | Working Days / Hours Confirmation Sent to LPA | Working Days / Hours Confirmation Accepted by LPA | Surface Water Drainage Plan Sent to LPA | Surface Water Drainage Plan Accepted by LPA | Noise / Accoustics Mitigation Plan Sent to LPA | Noise / Accoustics Mitigation Plan Accepted by LPA | Commencement Notice Sent to LPA | FP Compliance Submitted | FP Compliance Completed | Count of Compliance Items per site | Notes |  | Total Firm and f/c Demand | Firm Demand No. of Operators | eir Mobile | VF Nom | VF Tag | Three (3Irl) | Other Operator 1 | Tetra Ireland | Enet |  |  | Forecast Demand No. of Operators | eir Mobile | VF | VF Tag | Three (3Irl) | Other Operator 1 | Customer Demand (By Quarter / Year) | DEMAND STATUS FOR GATING | EARLIEST FC DEMAND?? | FP Final Decision Forecast | Blocker/Stop Details | Forecasted Gated Date | Site Gated | Gating Status | RFI Priority # | Development Category | Structure (+ FAS) Ordered | Reporting Proposed Structure Type | Structure Supplier | Structure Ready | Interface Steelwork Ordered | Interface Steelwork Ready | Power ESB Diversion Required | Power ESB Application Submitted | Power ESB Quote Received | Power ESB Quote Expiry Date | Power ESB Quote Approved (PO Approved) | Power ESB Survey | Power ESB Route & Solution Confirmed (For DD) | Power ESB Forecast | Power Temporary Connection Required Y/N | Power Temporary Connection Application Submitted | Power Temporary Connection Confirmed | Power Temporary Connection Forecast | SAR Required | SAR Provider | SAR Instructed | SAR Instructed Revision Counter | SAR Completed | SAR Completed Revision Counter | TL Site Survey Completed - DCP & CAT Scan | LUGS Required | RAMS for LUGS Surveys / Pre-Foundation Checks Completed | eir Notification Submitted for LUGS Survey / Pre-Foundation Checks | LUGS Survey / Pre-Foundation Works Start | LUGS Survey / Pre-Foundation Works Finish | LUGS Survey / Pre-Foundation Works Comment | SI / Technical Site Survey Required Y/N | RAMS for SI Surveys Completed | eir Notification Submitted for SI Survey | SI Survey Completed | SI Report Completed Forecast | SI Report Completed Actual | Piling Design Required | Piling Design Instructed | Piling Design Completed Forecast | Piling Design Completed Actual | Forecasted ICDD Date | ICDD | DD Provider | External DD Provider Site Survey | External DD Provider Site Survey Report Issued | DD Issued | DD Approved Forecast | DD Approved Actual Revision Count | DD Approved Actual | DD - Power Solution Completed - Sheet Added to/Included with DD | DRA Revision Count | DRA Issued | PHSP Revision Count | PHSP Issued | Appoint External Contractor | PCM Completed | PCM Revision Count | Construction Management Plan Completed | CMP Revision Count | Forecasted eir Notification Submitted | eir Notification Submitted N.B. 4 Weeks Notice | Notification Submitted Revision Count | VF Notification Issued (8 Weeks Notice) | Three Notification Issued (8 Weeks Notice) | eir Mobile Notification Issued (8 Weeks Notice) | TETRA Notification Issued (12 Weeks Notice) | Other Operator Notification Issued (8 Weeks TBC Notice) | ESB Notification Issued | HSA Notification Issued | ROL Submitted | ROL Expiry Date | FP Compliance Completed | Forecasted Start on Site | Start on Site | Enabling Works / Pre-Works Start | Enabling Works / Pre-Works Completed | Power Temporary Connection Civil Works Start | Power Temporary Connection Civil Works Completed | Power Independent Supply Civil Works Start | Power Independent Supply Civil Works Completed | Piling Works Start | Piling Works Completed | Foundation Civil Works Start | Foundation Civil Works Completed | Structure Start | Structure Erected | Interface Steelwork Installed | FAS Installed & Certified | Structure Completed | Cable Duct/Gantry Completed | RFI Forecast | RFI Forecast (By Qtr/Yr) | RFI Actual | Works Required | Works Required - Fencing / Landscaping - Planting / Re-instatement / Other | Works Completed | Redundant Structure to be Removed | Redundant Structure Details | Redundant Structure Removed (date) | Post- Construction Site Inspection Completed (PSCS) | Snag Report Issued (PSCS) | Snags Cleared (PSCS) | Construction Completion Pack Submitted (PSCS) | Construction Completion Pack Approved (PSDP) | Site Accepted (PSDP) | AB Drawing Completed (PSDP) | Site Residual Risk Report Completed (PSDP) | Site Safety File Updated & Completed (PSDP) | RADIX Updated | Handover to O&M Completed | Notes | Capex Budget Cost | UTS Label | Live Site | Site ID | Forecast RFI Date | RFI Actual | Proposed Structure Type | Portfolio | Gating status Comments | RFI Quarter | Current Development Plan (Gated/Live/UTS/Portfolio/FC RFI) | Gating Status | Site name | Current Structure Type | Current Height (m) | Proposed Structure Type | Proposed Height (m) | JR Issue Date | JR Current Status | JR Final Decision Date | JR Final Decision |  |  | FP Subm to Init Grant | mth | FP Subm to Final Grant | mth | Appeal Submission Date | Appeal Subm to ABP Decision | mth | ABP Final Decision Date
| TLKxxx | Site name | Limerick | EED | UID001 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice | 12 | Monopole | 24 |  |  | Option A |  | Limerick County | 3 |  | Yes | Charterhouse | OL | 2500 | 2020-04-06 | 2020-07-16 | [11 empty] | Amber |  |  | 2020-08-04 | 2020-08-04 | Yes | 20912 | Y | [7 empty] | 2020-11-20 | 2020-11-05 | GRANT |  | 2020-12-09 | 2020-12-09 | GRANT | 2020 | 2020-12-02 | [7 empty] | 2020-12-09 | Grant | 2020-12-09 | GRANT | 2025-12-08 | Final Grant | Part A (1) |  | 2022-07-12 |  | Complete | 1st Appl - success | [11 empty] | 11/08: Invalidated due to elevation requirement from LPA 22/07: Crozier change to Option A / B | No sound trees to be removed unless necessitated by the development | No | No | No | NB | No | YES | YES | [5 empty] | No | No | [25 empty] | 2022-08-19 | 2022-10-13 | 3 |  |  | 4 | 2 | 2022-11-29 | 2022-10-24 | [7 empty] | 2 |  |  |  | 2029-01-01 | 2024-01-01 |  | FP & Demand | 2024-01-01 | 2020-12-09 |  | 2020-12-16 | 2022-02-24 | RFI | [5 empty] | Yes | [37 empty] | 2020-12-26 | [5 empty] | 2021-02-14 | [12 empty] | 2021-02-24 | [11 empty] | 2022-10-13 | 2021-03-26 | 0 | [16 empty] | 2022-10-24 | Q4-2022 | 2022-10-24 |  |  |  | Yes | Lattice Tower - Openeir Equipment to be Relocated/Removed | [14 empty] | TLKxxx | Live | TLKxxx | 2022-10-24 | 2022-10-24 | Monopole | EED | 0 | Q4-2022 | 0 Live UTS EED Q4-2022 | RFI | Site name | Lattice | 12 | Monopole | 24 |  |  |  |  | - | - | 93 | 3.1 | 127 | 4.2333 | - | - | - | -
| TCxxxx | Site name | Cork | EED | UID002 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Tower | 15 | Lattice | 24 |  |  | Not Adjacent |  | Cork County | 2 |  | Yes | Charterhouse | OL | 2500 | 2020-02-25 | 2020-02-20 | Yes |  | 2020-03-06 | [8 empty] | Amber |  | Appeal | 2020-03-06 | 2020-03-06 | 2020-03-10 | 204496 | [8 empty] | 2020-06-17 | 2020-06-17 | GRANT | 1 | 2020-07-20 | 2020-07-20 | 3P APPEAL | 2020 | 2020-07-14 |  | 2020-07-20 | 307515 | 2020-11-10 |  | 2020-11-03 | GRANT | 2020-11-03 | Grant | 2020-11-03 | GRANT | 2025-11-02 | Final Grant | Part A (2) |  | 2022-10-05 |  | Complete | 1st Appl - success | [57 empty] | 3 | 1 |  | 2023-11-20 | [7 empty] | 2 | 2027-01-01 |  |  | 2026-01-01 |  |  | FP & Demand | 2026-01-01 | 2020-11-03 |  | 2020-11-10 | 2022-08-31 | RFI | [5 empty] | Yes | [33 empty] | Yes |  |  |  | 2020-11-20 | [5 empty] | 2021-01-09 | [12 empty] | 2021-01-19 | [11 empty] | - | 2021-02-18 | 0 | [7 empty] | Yes | [8 empty] | 2023-11-20 | Q4-2023 | 2023-11-20 |  |  |  | Yes | Lattice Tower | 2024-08-07 | [13 empty] | TCxxxx | Live | TCxxxx | 2023-11-20 | 2023-11-20 | Lattice | EED | 0 | Q4-2023 | 0 Live UTS EED Q4-2023 | RFI | Site name | Lattice Tower | 15 | Lattice | 24 |  |  |  |  | - | - | 103 | 3.4333 | 242 | 8.0667 | 2020-07-20 | 106 | 3.5333 | 2020-11-03
| TDUxxxx | Site name | Dublin | EED | UID268 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Monopole | 30 | Lattice | 36 |  |  |  |  | Fingal County | 1 |  | 2021-08-04 | LOC | Quayline | - | 2021-08-04 | 2021-08-09 | Yes |  | 2021-11-19 |  |  | Yes | FI |  | 2022-05-20 |  |  | Amber | FI |  | 2021-11-24 | 2021-11-24 | Yes | F21A/0640 | No | - | 2022-01-26 | 2022-10-24 | 2022-10-11 | - | - | - | 2022-11-21 | 2022-11-03 | GRANT | 1 | 2023-01-09 |  | 3P APPEAL | 2024 | 2022-11-30 |  | 2022-11-25 | 315201 | 2024-02-13 |  | 2024-01-24 | GRANT | 2024-02-13 | Grant | 2024-01-24 | GRANT | 2029-01-22 | Final Grant | Part A (144) |  |  |  | Complete | 1st Appl - success | [5 empty] | TJ | 2021-08-01 | [5 empty] | 1. Development shall be carried out and completed in accordance with the plans and particulars lodged with the application, as amended by the further plans submitted 11 Oct 2022. Where such conditions require agreement with the planning authority, the developer shall agree such details in writing prior to commencement of the development. 2. Surface Water drainage arrangements shall comply with the requirements of the planning authority for such services and works. 3. Prior to commencement, details of the proposed colour scheme for the strucuture and ancillary structures shall be submitted to and agreed in writing with the LPA. 4. No advertisement shall be erected or displayed on the proposed strucuture or its appendiges or within the curtilage of the site without a prior grant of planning permission. 5. The operator shall provide and make available the lattice tower fo co-location. | No | No | YES | No | No | No | No | [5 empty] | No | [31 empty] | 2 | 0 |  |  |  | existing | [5 empty] | 2 | 2027-01-01 |  |  |  | 2027-01-01 |  | FP / No Demand | 2027-01-01 | 2024-02-13 | 2027-01-01 | 2027-01-08 | [76 empty] | - |  | 0 | [16 empty] | 2027-02-07 | Q1-2027 | [21 empty] | Not Gated |  |  |  | Lattice | EED | 46388 | No Forcast Date | 46388 Not Gated UTS EED No Forcast Date | 0 |  | Monopole | 30 | Lattice | 36 |  |  |  |  | - | - | 344 | 11.4667 | 791 | 26.3667 | 2022-11-25 | 425 | 14.1667 | 2024-01-24
| TKKxxxx | Site name | Kilkenny | EED | UID180 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Mast | 50 | [6 empty] | Kilkenny County | [54 empty] | 0 |  | Part A (95) | [62 empty] | 1 | 0 | [9 empty] | 1 | 2028-01-01 | [5 empty] | No FP / No Demand | 2028-01-01 | 0 |  | 2028-01-01 | [76 empty] | - |  | 0 | [16 empty] | 2028-01-31 | Q1-2028 | [21 empty] | Not Gated |  |  |  | 0 | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | Lattice Mast | 50 | 0 | 0 |  |  |  |  | - | - | - | - | - | - | - | - | - | -
| TWWxxxx | Site name | Wicklow | EED | UID005 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice | 12 | Monopole | 24 |  |  |  |  | Wicklow County | 3 | 2029-11-02 |  | LOC | RC | 1000 | 2029-11-02 | [6 empty] | Yes | Application |  |  |  |  | Amber |  | Appeal | 2030-01-01 | [11 empty] | 2030-03-02 |  |  |  | 2030-04-06 |  |  | 2031 |  |  |  |  | 2031-04-01 | Grant |  |  | 2031-04-01 | Grant |  |  | 0 |  | 2 |  |  |  | Forecast | 2nd Appl | [57 empty] | 1 | 0 | [9 empty] | 1 | 2026-01-01 |  | 2026-01-01 |  |  |  | No FP / No Demand | 2026-01-01 | 2031-04-01 | [37 empty] | Yes | [9 empty] | 1900-01-09 | [5 empty] | 1900-02-28 | [12 empty] | 1900-03-10 | [11 empty] | - | 1900-04-09 | 0 | [16 empty] | 1900-06-08 | Q2-1900 | [21 empty] | Not Gated |  |  |  | Monopole | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | Lattice | 12 | Monopole | 24 |  |  |  |  | - | - | - | - | - | - | - | - | - | -
| TWWxxxx | Site name | Wicklow | EED | UID329 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice | 12 | Lattice | 24 |  |  |  |  | Wicklow County | 3 |  | 2022-09-30 | Charterhouse | RC | 1000 | 2022-09-30 | 2022-10-27 | 2022-11-14 |  | 2022-11-14 |  |  | Yes | Appeal | Yes | 2023-02-20 |  |  | Amber |  |  | 2022-11-16 | 2022-11-16 | Yes | 221229 | [8 empty] | 2023-05-17 | 2023-01-24 | REFUSED | 0 | 2023-06-21 |  | TL APPEAL | 2024 | 2023-02-20 | 2023-02-20 |  | 315860 | 2024-04-30 |  | 2024-04-09 | REFUSED | 2024-04-30 | Refusal | 2024-04-09 | REFUSED | 0 | Refused | 3A |  |  |  | Archive | 1st Appl - failed | [198 empty] | Not Gated |  |  |  | Lattice | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | Lattice | 12 | Lattice | 24 |  |  |  |  | - | - | 69 | 2.3 | 510 | 17 | 2023-02-20 | 414 | 13.8 | 2024-04-09
| TWHxxxx | Site name | Westmeath | EED | UID306 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Tower | 15 | Lattice | 20 | Monopole | 21 |  |  | Westmeath County | 1 |  | 2020-08-07 | Charterhouse | RC | 1000 | 2020-08-07 | 2020-09-11 |  |  | 2020-10-27 |  |  | Yes | FI | Yes |  |  |  | Green | FI |  | 2020-10-30 | 2020-10-30 | Yes | 206309 | No | - | 2021-01-05 | 2021-10-03 | 2021-09-21 | - | - | - | 2021-10-29 | 2021-10-18 | GRANT | 0 | 2021-11-24 | 2021-11-24 | GRANT | 2021 | 2021-11-14 | [7 empty] | 2021-11-24 | Grant | 2021-11-24 | GRANT | 2026-11-23 | Final Grant | Part A (161) |  | 2022-05-31 |  | Complete | 1st Appl - success |  |  |  |  | 2020-12-08 | [6 empty] | Limited ground space for development | The development shall be carried out strictly in accordance with the plans and details received with the planning application. The applicant is responsible for the repairs of any damage caused to the public footpath and roadway as a direct result of the development works. Prior to the commencement of development, a Construction Environmental Management Plan shall be submitted for the written agreement of the planning authority. On decommissioning of the telecommunications service, or if the service ceases operation for a period of more than one year, the telecommunications structure including foundations and access arrangements shall be removed and the site lands shall be reinstated on removal of the telecommunications structure and ancillary structures within three months of decommissioning at the operators expense. Unless otherwise agreed in writing with the planning authority, the applicant shall engage with the planning authorityin respect of the erection of a low intensity fixed red obstacle light which shall be fitted as close to the top of the mast as practicable and shall be visible from all angles in azimuth. | No | No | No | No | No | YES | No | No | No | No | No | No | No | N.B. Damage to footpath | n/a | n/a | 2024-08-19 | 2024-08-26 | n/a | n/a | n/a | n/a | n/a | n/a | 2024-08-23 | 2024-11-13 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2024-09-17 | 2024-11-13 | 2 |  |  | 3 | 1 |  | 2021-09-09 | [7 empty] | 2 | 2026-01-01 |  |  | 2030-01-01 |  |  | FP & Demand | 2026-01-01 | 2021-11-24 |  | 2022-02-24 | 2022-02-24 | RFI | 102 | Replacement | TBC |  | TBC | TBC |  |  | TBC | [11 empty] | Yes | Delmec | 2024-04-09 |  | 2024-04-24 |  | 2021-03-03 | Yes | 2024-04-11 | 2024-04-12 | 2024-05-15 | 2024-05-16 | Cables noted while surveying site & they need to be moved | Yes | 2024-04-11 | 2024-04-12 | 2024-05-16 | 2024-05-31 | 2024-06-11 | Yes | 2024-06-14 | 2024-07-25 |  | 2022-03-06 | 2024-04-11 | Delmec | 2024-05-16 | 2024-06-03 | 2024-07-31 | 2024-08-02 | 4 | 2024-08-26 | ESB Independent Power Supply Solution issued with DD | 2 | 2024-08-02 | 2 | 2024-08-02 | n/a | 2024-08-26 | 2 | 2024-08-29 | 2 | 2024-08-12 | 2024-08-30 | 2 | [9 empty] | 2024-11-13 | 2024-09-11 | 2024-08-12 | 2024-08-12 | 2024-08-16 |  |  |  |  | 2024-11-26 | 2024-11-29 | 2024-12-09 | 2024-12-13 | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-22 | Q1-2025 | [5 empty] | Wooden Pole - VF Equipment to be Removed | [14 empty] | TWHxxxx | Live | TWHxxxx | 2025-01-22 |  | Lattice | EED | 0 | Q1-2025 | 0 Live UTS EED Q1-2025 | RFI | Site name | Lattice Tower | 15 | Lattice | 20 |  |  |  |  | - | - | 353 | 11.7667 | 390 | 13 | - | - | - | -
| TCNxxxx | Site name | Cavan | EED | UID007 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Lattice | 24 |  |  | Hot Swap |  | Cavan County | 2 |  | Yes | LOC | focus + | 2500 | 2020-05-27 | 2020-06-16 |  |  | 2021-02-25 |  |  | Yes | Application | Yes | 2021-01-11 |  |  | Amber | FI | Appeal | 2021-03-11 | 2021-03-11 | 2021-03-12 | 21128 | [8 empty] | 2021-05-13 | 2021-05-05 | REFUSED | 15+ | 2021-06-17 |  | TL APPEAL | 2022 | 2021-06-01 | 2021-06-01 |  | 310372 | 2021-10-04 |  | 2022-02-16 | GRANT | 2022-02-16 | Grant | 2022-02-16 | GRANT | 2027-02-15 | Final Grant | Part A (5) |  | Yes |  | Complete | 1st Appl - success | [11 empty] | 05/10/2022: Notification issued by email to LPA for temporary installation | Details of removal of telecommunications structure and reinstatement of site to be submitted for agreement prior to commencement of development - TL planner to submit that should only apply if permitted structure is being removed in future and details will be submitted in that instance prior to its removal. No advertisements on structure or site without planning permission. Aircraft Warning Light to be installed - this requirement to be submitted to IAA for review | No | YES | No | No | No | No | No | [5 empty] | No | No | [6 empty] | n/a | n/a | [17 empty] | 2022-07-25 |  | 1 |  |  | 3 | 2 | 2023-05-15 | 2023-05-15 | [7 empty] | 1 |  |  |  | 2026-01-01 |  |  | FP & Demand | 2026-01-01 | 2022-02-16 |  | 2022-02-23 | 2022-02-24 | RFI | [5 empty] | Yes | [37 empty] | 2022-03-05 | [5 empty] | 2022-04-24 | [12 empty] | 2022-05-04 | [11 empty] | - | 2022-06-03 | 0 | [16 empty] | 2023-05-15 | Q2-2023 | 2023-05-15 |  |  |  | Yes | Wooden Pole | 2023-04-17 | [13 empty] | TCNxxxx | Live | TCNxxxx | 2023-05-15 | 2023-05-15 | Lattice | EED | 0 | Q2-2023 | 0 Live UTS EED Q2-2023 | RFI | Site name | Wooden Pole | 12 | Lattice | 24 |  |  |  |  | - | - | 55 | 1.8333 | 342 | 11.4 | 2021-06-01 | 260 | 8.6667 | 2022-02-16
| TMHxxxx | Site name | Meath | EED | UID008 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 10 | Monopole | 18 |  |  |  | No title, TLM Green. Omni & GPS | Meath County | 2 |  | 2021-07-30 | LOC | Marcin | - | 2021-07-30 | 2021-08-24 | Yes |  | 2021-11-19 | [8 empty] | Amber |  |  | 2021-11-30 | 2021-11-30 | Yes | 212282 | No | - | 2022-02-03 | 2022-11-02 | 2022-10-18 | - | - | - | 2022-12-16 | 2022-12-09 | GRANT | 1 | 2023-01-30 | 2023-01-30 | GRANT | 2023 | 2023-01-05 | [7 empty] | 2023-01-30 | Grant | 2023-01-30 | GRANT | 2028-01-29 | Final Grant | 3B |  | 2023-06-16 |  | Complete | 1st Appl - success | Y |  |  | Subject to Agreement |  | TJ | 2021-07-01 |  | Ontower |  |  |  | The development shall be carried out in accordance with plans and particulars lodged with the planning application. No material change of use of the telecommunications equipment and support structures shall be made without a prior grant of planning permission. The antenna and mounting configuration shall be in accordance with the details submitted with this application and shall not be altered without a prior grant of planning permission. The applicant shall provide and make available at reasonable terms the proposed telecommunications structure for the provision of mobile telecommunications antenna of third party licenced mobile telecommunications operators. In the event of the proposed structure becoming obsolete and being decommissioned, the applicant shall at their own expense, remove the mast and antennae and return the site to its original condition. | No | No | No | No | No | No | No | [5 empty] | No | N.B. Debris deposit, damage to public road, adequate off carriageway parking facilities, and disposal of waste material. |  |  | n/a | n/a | n/a | n/a | n/a | n/a | [22 empty] | 3 | 1 |  | 2022-10-20 | [7 empty] | 2 | 2027-01-01 |  |  | 2027-01-01 |  |  | FP & Demand | 2027-01-01 | 2023-01-30 | FP OPW | 2023-05-10 | 2023-05-10 | Stop |  | Replacement |  |  | GSM | Yes |  |  | TBC | [17 empty] | TBC | [6 empty] | Yes | 2023-05-29 | 2023-06-01 | On hold - OPW | [8 empty] | Delmec | [16 empty] | 1900-01-09 | [11 empty] | - | 1900-02-08 | 0 | [16 empty] | 1900-04-09 | Q2-1900 | [20 empty] | TMHxxxx | Live | TMHxxxx |  |  | Monopole | EED | FP OPW | No Forcast Date | FP OPW Live UTS EED No Forcast Date | Stop | Site name | Wooden Pole | 10 | Monopole | 18 |  |  |  |  | - | - | 374 | 12.4667 | 426 | 14.2 | - | - | - | -
| TLKxxxx | Site name | Limerick | TC68 | UID009 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Modular Monopole | 12 |  |  |  | 3 pole cluster, TLM Green. 2 omni, 1dish | Limerick County | 3 |  |  | LOC | RC | 2500 | [13 empty] | Amber | [31 empty] | Refusal |  |  | 0 |  | Part B (2) |  |  |  | Forecast | 2nd Appl | Y | State Owned - OPW | OPW | Subject to Agreement | [53 empty] | 2 | 1 |  | 2021-12-02 | [7 empty] | 1 |  | 2029-01-01 |  |  |  |  | No FP & Demand | 2029-01-01 | 0 | No FP OPW | 2029-01-01 | [76 empty] | - |  | 0 | [16 empty] | 2029-05-01 | Q2-2029 | [21 empty] | Not Gated |  |  |  | Modular Monopole | TC68 | No FP OPW | No Forcast Date | No FP OPW Not Gated UTS TC68 No Forcast Date | 0 |  | Wooden Pole | 12 | Modular Monopole | 12 |  |  |  |  | - | - | - | - | - | - | - | - | - | -
| TGYxxxx | Site name | Galway | TC68 | UID010 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Mast | 15 | Monopole | 21 |  |  | Not Adjacent |  | Galway County | 2 |  | 2020-01-13 | Entrust | RC | 1000 | 2020-02-03 | 2020-02-03 |  |  | 2020-05-08 |  |  | Yes | Application | Yes | Yes | Y |  | Red | FI | Appeal | 2021-05-21 | 2021-05-21 | Yes | 21940 | [8 empty] | 2021-11-17 | 2021-07-23 | GRANT |  | 2021-08-30 | 2021-08-30 | GRANT | 2021 | 2021-08-19 | [7 empty] | 2021-08-30 | Refusal | 2021-08-30 | GRANT | 2026-08-29 | Final Grant | Part A (6) |  | 2023-09-13 |  | Complete | 1st Appl - success | [11 empty] | 19/04/21: Change from 24m Lattice to 21m monopole | 1. Develop according to plans submitted. 2. Remove existing Lattice. 3. Remove Structure when obsolete. 4. Inform LPA if ownership changes. 5. Additional planning required if structure is to be used for something else. 6. Cannot advertise structure prior to Final Grant. 7 i. Implement a system to monitor radiation and undertake periodically. 7 ii. Comply with radiation guidelines. 8 i. Make available the strucutre for MNOs to co-locate. 8 ii. Make available space on site equipment for multiple MNOs if required. 9 i. Dispose of Surface water. 9 ii. Do not impair existing drainage. 10 i. Submit Traffic Management Plan. 10 ii. Maintain Sight Distance triangles. 10 iii. Obtain a Road Opening Licence is adjacent to public road. 10 iv. Prevent spillage and debris on adjoining roads during construction. | No | No | No | No | YES | No | No | [5 empty] | No | N.B. Drainage, Noise Pollution, Working hours regualtions. |  |  | n/a | n/a | n/a | n/a | n/a | n/a | [17 empty] | 2023-11-03 | 2024-02-14 | 2 |  | existing | 3 | 1 | 2024-03-26 |  | 2024-03-28 | [6 empty] | 2 |  |  |  | 2027-01-01 | 2026-01-01 |  | FP & Demand | 2026-01-01 | 2021-08-30 |  | 2021-09-06 | 2023-12-06 | RFI | 87 | Replacement | 21m Monopole |  | GSM 01 | Yes | N/A |  | No | [18 empty] | Yes | 2023-09-14 | 2023-09-14 | Not Required | Not Required |  |  | - | - | - | [6 empty] | 2021-09-16 | 2023-09-20 | TL | - | - | 2023-10-02 | 2023-10-06 |  | 2023-10-06 | Temp Power Supply Solution issued with DD |  | 2023-10-12 |  | 2023-10-12 | n/a | 2023-10-06 |  | 2023-12-11 |  | 2023-10-16 | 2023-12-14 |  | N.B. | - | - | - | - | - | - |  |  | 2024-02-14 | 2023-11-15 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-26 | 2024-03-01 |  |  |  |  | 2024-02-26 | 2024-03-01 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-26 | Q1-2024 | 2024-03-26 | Yes | Reinstatement - Yard | 2024-05-22 | Yes | Lattice Tower | 2024-10-01 | [6 empty] | 2024-04-03 | [6 empty] | TGYxxxx | Live | TGYxxxx | 2024-03-26 | 2024-03-26 | Monopole | TC68 | 0 | Q1-2024 | 0 Live UTS TC68 Q1-2024 | RFI | Site name | Lattice Mast | 15 | Monopole | 21 |  |  |  |  | - | - | 63 | 2.1 | 101 | 3.3667 | - | - | - | -
| TLKxxxx | Site name | Limerick | TC68 | UID011 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Tower | 12 | Lattice ext | 20 |  |  | Extension |  | Clare County | 2 |  | Yes | Charterhouse | OL | 2500 | 2019-09-30 | 2020-08-13 |  |  | 2020-09-01 | [8 empty] | Amber |  | Appeal | 2020-10-16 | 2020-10-16 | 2020-10-21 | 20770 | [8 empty] | 2020-12-15 | 2020-12-14 | REFUSED | 5 | 2021-01-19 |  | TL APPEAL | 2021 | 2021-01-10 | 2021-01-19 |  | 309257 | 2021-05-24 |  | 2021-05-05 | GRANT | 2021-05-05 | Grant | 2021-05-05 | GRANT | 2026-05-04 | Final Grant | Part A (7) |  | 2021-07-09 |  | Complete | 1st Appl - success |  |  |  |  | 2020-11-24 | [5 empty] | Y | 30/10/2019: Nil FP Required ATT - Foundation / Tower Strengthening TBC | Colour scheme for structure, ancillary structures and fencing to be submitted and agreed in writing with LPA prior to commencement. | No | No | YES | No | No | No | No | [5 empty] | No | No |  |  | n/a | n/a |  |  | n/a | n/a | [17 empty] | 2021-12-02 | 2022-02-10 | 1 |  |  | 2 | 1 |  | 2022-10-31 | [7 empty] | 1 |  |  |  | 2030-01-01 |  |  | FP & Demand | 2030-01-01 | 2021-05-05 |  | 2021-05-12 | 2021-07-09 | RFI | [5 empty] | Yes | [37 empty] | 2021-05-22 | [5 empty] | 2021-07-11 | [12 empty] | 2021-07-21 | [11 empty] | 2022-02-10 | 2021-08-20 | 0 | [16 empty] | 2022-01-31 | Q1-2022 | 2022-01-31 |  |  |  | n/a | [15 empty] | TLKxxxx | Live | TLKxxxx | 2022-01-31 | 2022-01-31 | Lattice ext | TC68 | 0 | Q1-2022 | 0 Live UTS TC68 Q1-2022 | RFI | Site name | Lattice Tower | 12 | Lattice ext | 20 |  |  |  |  | - | - | 59 | 1.9667 | 201 | 6.7 | 2021-01-19 | 106 | 3.5333 | 2021-05-05
| TLMxxxx | Site name | Leitrim | TC68 | UID193 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Monopole | 25 | Lattice | 30 |  |  |  |  | Leitrim County | 2 |  | 2021-11-22 | Charterhouse | Quayline | - | 2021-11-22 | 2021-12-06 | Yes |  | 2021-12-13 | [8 empty] | Amber | FI |  | 2021-12-15 | 2021-12-15 | Yes | 21265 | No | - | - | - | - | - | - | - | 2022-06-13 | 2022-02-21 | GRANT |  | 2022-07-18 |  | 3P APPEAL | 2022 | 2022-03-20 |  | 2022-03-16 | 313037 | 2022-07-19 |  | 2022-05-26 | GRANT | 2022-05-26 | Grant | 2022-05-26 | GRANT | 2027-05-25 | Final Grant | 3f |  |  |  | Complete | 1st Appl - success | [5 empty] | TJ | 2021-08-01 | [47 empty] | - |  |  | 1 | 0 |  |  | 2024-07-23 | [6 empty] | 1 | 2026-09-01 | [5 empty] | FP / No Demand | 2026-09-01 | 2022-05-26 | On Hold - ROI | 2026-09-01 | [76 empty] | - |  | 0 | [16 empty] | 2027-02-28 | Q1-2027 | [21 empty] | Not Gated |  |  |  | Lattice | TC68 | On Hold - ROI | No Forcast Date | On Hold - ROI Not Gated UTS TC68 No Forcast Date | 0 |  | Monopole | 25 | Lattice | 30 |  |  |  |  | - | - | 68 | 2.2667 | 162 | 5.4 | 2022-03-16 | 71 | 2.3667 | 2022-05-26
| TMOxxxx | Site name | Mayo | TC68 | UID014 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Monopole | 15 | Monopole | 21 |  |  |  |  | Mayo County | 2 |  | 2021-08-04 | Charterhouse | focus + | - | 2021-08-04 | 2021-08-13 | Yes |  | 2021-09-22 | [8 empty] | Green | FI | Appeal | 2021-09-30 | 2021-09-30 | Yes | 211056 | No | - | - | - | - | - | - | - | 2022-03-29 | 2021-11-24 | GRANT | 0 | 2021-12-28 | 2021-12-28 | GRANT | 2021 | 2021-12-21 | [7 empty] | 2021-12-28 | Grant | 2021-12-28 | GRANT | 2026-12-27 | Final Grant | 3f |  |  |  | Complete | 1st Appl - success | [5 empty] | TJ | 2021-07-01 | [47 empty] | - |  |  | 0 | 0 | [9 empty] | 0 | [6 empty] | FP / No Demand | - | 2021-12-28 | FP No Demand | [65 empty] | 1900-01-09 | [11 empty] | - | 1900-02-08 | 0 | [16 empty] | 1900-04-09 | Q2-1900 | [21 empty] | Not Gated |  |  |  | Monopole | TC68 | FP No Demand | No Forcast Date | FP No Demand Not Gated UTS TC68 No Forcast Date | 0 |  | Monopole | 15 | Monopole | 21 |  |  |  |  | - | - | 55 | 1.8333 | 89 | 2.9667 | - | - | - | -
| TLMxxxx | Site name | Leitrim | TC68 | UID075 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Mast | 14 | Lattice ext | 20 |  |  |  |  | Leitrim County | 2 |  | 2020-02-10 | LOC | RC | 1000 | 2024-02-09 | 2024-07-08 | Yes | 5 | 2024-07-24 | 2024-06-25 | 2024-07-25 | Yes | Application |  | 2024-07-26 |  |  | Amber | FI | Appeal | 2024-07-26 | 2024-07-31 | 2024-08-07 | 2460158 | [8 empty] | 2024-08-30 | 2024-09-30 | REFUSED | 2 | 2024-10-04 | 2024-09-30 | REFUSED | 2026 | 2024-10-29 |  |  |  | 2025-09-29 | Grant |  |  | 2025-09-29 | Grant | 2024-09-30 | REFUSED | 0 | Refused | Part A (44) |  |  |  | Archive | Plan B | [6 empty] | #N/A | [50 empty] | 1 | 1 |  | 2021-12-02 | [7 empty] | 0 | [6 empty] | No FP & Demand | - | 2025-09-29 |  | 2025-10-06 | [64 empty] | 1900-01-09 | [11 empty] | - |  | 0 | [16 empty] | 1900-02-28 | Q1-1900 | [21 empty] | Not Gated |  |  |  | Lattice ext | TC68 | 0 | No Forcast Date | 0 Not Gated UTS TC68 No Forcast Date | 0 |  | Lattice Mast | 14 | Lattice ext | 20 |  |  |  |  | - | - | 61 | 2.0333 | 61 | 2.0333 | - | - | - | -
| TLKxxx | Site name | Mayo | TC68 | UID017 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Monopole | 21 |  |  | Not Adjacent |  | Mayo County | 3 |  | Yes | Charterhouse | RC | 2500 | 2020-08-31 | 2020-09-21 |  |  | 2020-10-15 |  |  | Yes | FI | Yes | Yes | 2021-05-25 |  | Red | FI | Appeal | 2020-10-16 | 2020-10-16 | 2020-10-19 | 20779 |  |  | 2020-12-10 | 2021-09-09 | 2021-05-28 |  |  |  | 2021-08-01 | 2021-07-28 | REFUSED | 4 | 2021-09-05 |  | TL APPEAL | 2023 | 2021-08-24 | 2021-08-23 |  | 311200 | 2022-01-04 |  | 2023-01-23 | Grant | 2023-01-23 | Refusal | 2023-01-23 | GRANT | 2028-01-22 | Final Grant | Part A (10) |  | Yes |  | Complete | 1st Appl - success |  |  |  |  | 2020-11-22 | [6 empty] | Limited Ground Space - No Space for Ground equipment | Development to be carried out in accordance with plans. Development as per described in public notices. Structure to be made available to third party telecommunications operators. Within 6 months of the cessation of the use of the structure, all structures to be removed from the site and reinstated in accordance with a scheme to be agreed with the Planning Authority as soon as is practicable. Colour scheme to be submitted and agreed with Planning Authoirty prior to commencement of development. A low intensity fixed red obstacle light to be fitted to the top of the mast. No advertising on the strucutre or within the site. Site development and building works to be carried out within prescribed hours. | No | YES | YES | No | No | No | No | [5 empty] | No | No | [5 empty] | No response | n/a | n/a | [17 empty] | 2023-03-21 | 2023-05-30 |  |  |  | 1 | 1 |  | 2023-12-18 | [7 empty] | 0 | [6 empty] | FP & Demand | - | 2023-01-23 |  | 2023-01-30 | 2023-02-17 | RFI | [5 empty] | Yes | [33 empty] | Yes |  |  |  | 2023-02-09 | [5 empty] | 2023-03-31 | [12 empty] | 2023-04-10 | [11 empty] | 2023-05-30 | 2023-05-10 | 0 | [7 empty] | Yes | [8 empty] | 2023-12-18 | Q4-2023 | 2023-12-18 |  |  |  | Yes | Wooden Pole | 2024-05-22 | [13 empty] | TLKxxx | Live | TLKxxx | 2023-12-18 | 2023-12-18 | Monopole | TC68 | 0 | Q4-2023 | 0 Live UTS TC68 Q4-2023 | RFI | Site name | Wooden Pole | 12 | Monopole | 21 |  |  |  |  | - | - | 285 | 9.5 | 829 | 27.6333 | 2021-08-23 | 518 | 17.2667 | 2023-01-23
| TCxxxx | Site name | Westmeath | TC68 | UID097 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Monopole | 15 |  |  |  | WP TLM Red, empty | Westmeath County | 3 |  | Yes | Charterhouse | OL | 1000 | Yes | 2020-11-17 |  |  | 2020-11-20 | [8 empty] | Green |  |  | 2020-11-27 | 2020-11-27 | Yes | 206334 | No | - | - | - | - | - | - | - | 2021-02-02 | 2021-02-01 | GRANT | 0 | 2021-03-11 | 2021-03-11 | GRANT | 2021 | 2021-02-28 | [7 empty] | 2021-03-11 | Grant | 2021-03-11 | GRANT | 2026-03-10 | Final Grant | Part A (56) |  |  |  | Complete | 1st Appl - success |  |  |  |  | 2021-01-12 | [8 empty] | No | No | No | No | No | YES | No | [5 empty] | No | Footpath to be agreed in writing. |  |  | n/a | n/a | n/a | n/a | n/a | n/a | [19 empty] | 2 |  |  | 1 | 0 | [9 empty] | 1 |  |  |  | 2025-08-01 |  |  | FP / No Demand | 2025-08-01 | 2021-03-11 | FP No Demand | 2025-08-01 | 2025-08-08 | [75 empty] | - |  | 0 | [16 empty] | 2026-02-04 | Q1-2026 | [20 empty] | TCxxxx | Live | TCxxxx | 2026-02-04 |  | Monopole | TC68 | FP No Demand | Q1-2026 | FP No Demand Live UTS TC68 Q1-2026 | 0 | Site name | Wooden Pole | 12 | Monopole | 15 |  |  |  |  | - | - | 66 | 2.2 | 104 | 3.4667 | - | - | - | -
| TDUxxxx | Site name | Wexford | TC68 | UID019 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 10 | Lattice | 20 |  |  | Not Adjacent |  | Wexford County | 1 |  | Yes | LOC | RC | 2500 | 2020-02-10 | 2020-03-10 |  |  | 2020-05-11 | [8 empty] | Green |  |  | 2020-11-18 | 2020-11-18 | Yes | 20201383 | [8 empty] | 2021-01-20 | 2021-01-15 | GRANT | 2 | 2021-02-08 | 2021-02-08 | 3P APPEAL | 2021 | 2021-02-11 |  | 2021-02-02 | 309348 | 2021-06-08 |  | 2021-06-03 | GRANT | 2021-06-03 | Grant | 2021-06-03 | GRANT | 2026-06-02 | Final Grant | Part A (12) |  | Yes |  | Complete | 1st Appl - success | [57 empty] | 3 | 1 |  | 2022-07-29 | [7 empty] | 2 | 2027-01-01 |  |  | 2028-01-01 |  |  | FP & Demand | 2027-01-01 | 2021-06-03 |  | 2021-06-10 | 2021-08-31 | RFI | [5 empty] | Yes | [37 empty] | 2021-06-20 | [5 empty] | 2021-08-09 | [12 empty] | 2021-08-19 | [11 empty] | - | 2021-09-18 | 0 | [16 empty] | 2022-07-29 | Q3-2022 | 2022-07-29 |  |  |  | Yes | Wooden Pole | 2024-04-10 | [13 empty] | TDUxxxx | Live | TDUxxxx | 2022-07-29 | 2022-07-29 | Lattice | TC68 | 0 | Q3-2022 | 0 Live UTS TC68 Q3-2022 | RFI | Site name | Wooden Pole | 10 | Lattice | 20 |  |  |  |  | - | - | 58 | 1.9333 | 197 | 6.5667 | 2021-02-02 | 121 | 4.0333 | 2021-06-03
| TKKxxxx | Site name | Galway | TC68 | UID004 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Modular Monopole | 12 |  |  |  |  | Galway County | 3 |  |  | LOC | RC |  | 2026-08-16 | [6 empty] | Yes | Application |  |  |  |  | Amber |  | Appeal | 2026-10-15 | [11 empty] | 2026-12-14 |  |  |  | 2027-01-18 |  |  | 2028 |  |  |  |  | 2028-01-13 |  |  |  | 2028-01-13 | Grant |  |  | 0 |  | Part B (1) |  |  |  | Forecast | 1st Appl | Y | State Owned - OPW | OPW | Subject to Agreement |  | TJ | 2021-11-01 |  |  |  |  | 14/04/21: REVIEW EXEMPTION SWAP Red line" Works Area" for Planning Drawing differs from "TL Site Area" on Crozier Drawing - ONLY for planning application purposes | [45 empty] | 1 | 0 | existing | [8 empty] | 1 |  | 2028-01-01 |  |  |  |  | No FP / No Demand | 2028-01-01 | 2028-01-13 | No FP OPW | 2028-01-01 | [76 empty] | - |  | 0 | [16 empty] | 2028-04-30 | Q2-2028 | [21 empty] | Not Gated |  |  |  | Modular Monopole | TC68 | No FP OPW | No Forcast Date | No FP OPW Not Gated UTS TC68 No Forcast Date | 0 |  | Wooden Pole | 12 | Modular Monopole | 12 |  |  |  |  | - | - | - | - | - | - | - | - | - | -
| TWWxxxx | Site name | Galway | TC68 | UID012 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Monopole | 18 |  |  |  | TLM red vf & ti | Galway County | 3 |  | 2022-03-31 | Charterhouse | Quayline | - | 2022-03-31 | 2022-04-19 |  |  | 2022-05-13 | [8 empty] | Amber |  |  | 2022-05-18 | 2022-05-18 | 2022-05-20 | 22649 | No | - | - | - | - | - | - | - | 2022-07-27 | 2022-07-13 | REFUSED | 2 | 2022-08-31 |  | TL APPEAL | 2024 | 2022-08-09 | 2022-08-09 |  | 314308 | 2024-02-12 |  | 2023-10-26 | REFUSED | 2023-11-01 | Grant | 2023-10-26 | REFUSED | 0 | Refused | Part A (8) |  | 2023-11-17 |  | Archive | 1st Appl - failed | [5 empty] | TJ | 2022-03-01 | [5 empty] | 1. Development to be carried out in accordance with Plans. Where conditions require details to be agreed with the planning authority, developer shall agree such details in writing. 2. Developer shall make proposed structure available to third party operators. 3. Within six months of cessation of use of telecoms structure, all structures permitted under this permission shall be removed and site reinstated at operators expense. 4. The 12 Metre High Wooden Pole (RR - VF presently located on this) shall be removed from the site within 6 months of the new monopole becoming operational. 5. Prior to commencement of the development, details of tree planting along the fornt/western boundary of the site shall be agreed in writing with the planning authority. 6. Prior to commencement of the development, details of the proposed Colour Scheme for the strucuture and ancillary structures shall be submitted to and agreed in writing with the planning authoirty. 7. A low intensity fixed red obstacle light shall be fitted as close to the top of the mast as practicable and shall be visible from all angles in azimuth. 8. No advertisement or advertisement structure shall be erected or displayed on the proposed structure or on the site. 9. Site Development 0800 to 1900 Monday to Friday, 0800 to 1400 Saturday, None on Sundays and Public Holidays. Deviation from these times only allowed in exceptional circumstances where prior written approval received from the planning authority. | No | YES | YES | YES | No | No | No | [5 empty] | No | No |  |  |  |  | 2023-12-06 | 2024-01-10 | 2023-12-06 | 2024-01-10 | [17 empty] | 2023-12-06 | 2024-01-11 |  |  |  | 3 | 1 |  | 2021-10-08 | [7 empty] | 2 | 2029-01-01 |  |  | 2028-01-01 |  |  | No FP & Demand | 2027-01-01 | 2023-11-01 | Stop - JR | 2026-09-01 | 2026-09-08 | Stop |  | Replacement | 18m Monopole |  | GSM | No | Shorter Standoffs to be ordered. Platforms to be removed |  | TBC | [17 empty] | TBC | Yes | 2023-12-04 |  | TBC |  |  | Yes | 2023-12-04 | 2023-12-04 | [26 empty] | 1900-01-09 | [11 empty] | 2024-01-11 | 1900-02-08 | 0 | ESB Diversion TBC | [15 empty] | 2027-03-07 | Q1-2027 |  | Yes | Landscape - Planting January - March 2025 TBC |  |  | Wooden Pole | [14 empty] | TWWxxxx | Live | TWWxxxx | 2027-03-07 |  | Monopole | TC68 | Stop - JR | Q1-2027 | Stop - JR Live UTS TC68 Q1-2027 | Stop | Site name | Wooden Pole | 12 | Monopole | 18 | 2023-12-20 | Complete | 2024-10-14 | Quashed | 299 | 9.9667 | 56 | 1.8667 | 526 | 17.5333 | 2022-08-09 | 443 | 14.7667 | 2023-10-26
| TWWxxxx | Site name | Cork | 108 | UID022 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 10 | Lattice | 20 |  |  | Not Adjacent |  | Cork County | 1 |  | Yes | Charterhouse | RC | 2500 | 2019-10-21 | 2020-08-11 |  |  | 2020-09-14 | [8 empty] | Green |  |  | 2020-09-18 | 2020-09-18 | Yes | 206114 | [8 empty] | 2020-11-13 | 2020-11-19 | GRANT | 0 | 2020-12-23 | 2020-12-23 | GRANT | 2020 | 2020-12-16 | [7 empty] | 2020-12-23 | Grant | 2020-12-23 | GRANT | 2025-12-22 | Final Grant | Part A (15) |  | Yes |  | Complete | 1st Appl - success | [11 empty] | 20/11/2019: Site to be reviewed for Cust uptake by AM - possible customer uptake for NBI | Details and drawings of proposed retaining wall to be submitted prior to commencement of development. Landscaping Scheme to be submitted and agreed prior to commencement of development. | No | No | No | YES | NB Parking | No | No | [5 empty] | No | Drawing and details of retaining wall to be agreed with LPA |  |  | n/a | n/a | n/a | n/a | 2022-07-26 | 2022-09-14 | [17 empty] | 2022-07-26 | 2022-09-14 | 3 |  |  | 1 | 1 |  | 2022-10-13 | [7 empty] | 0 | [6 empty] | FP & Demand | - | 2020-12-23 |  | 2020-12-30 | 2021-01-26 | RFI | [39 empty] | Yes |  |  |  | 2021-01-09 | [5 empty] | 2021-02-28 | [12 empty] | 2021-03-10 | [11 empty] | 2022-09-14 | 2021-04-09 | 0 | [7 empty] | Yes | [8 empty] | 2022-10-13 | Q4-2022 | 2022-10-13 |  |  |  | Yes | Wooden Pole - VF Tx Parallel Build Required then VF Omni Antenna & Tx Link Dish & Wooden Pole to be Removed by TL | [14 empty] | TWWxxxx | Live | TWWxxxx | 2022-10-13 | 2022-10-13 | Lattice | 108 | 0 | Q4-2022 | 0 Live UTS 108 Q4-2022 | RFI | Site name | Wooden Pole | 10 | Lattice | 20 |  |  |  |  | - | - | 62 | 2.0667 | 96 | 3.2 | - | - | - | -
| TWHxxxx | Site name | Cork | 108 | UID023 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice | 20 | Lattice ext | 24 |  |  |  |  | Cork County | 1 | 2025-12-08 |  | LOC | RC | 2500 | 2025-12-08 | [12 empty] | Amber |  | Appeal | 2026-02-06 | [11 empty] | 2026-04-07 |  |  |  | 2026-05-12 |  |  | 2027 |  |  |  |  | 2027-05-07 |  |  |  | 2027-05-07 | Grant |  |  | 0 |  | Part A (15) |  |  |  | Forecast | Plan B | [57 empty] | 0 | 0 | [9 empty] | 0 | [6 empty] | No FP / No Demand | - | 2027-05-07 | [47 empty] | 1900-01-09 | [5 empty] | 1900-02-28 | [12 empty] | 1900-03-10 | [11 empty] | - | 1900-04-09 | 0 | [16 empty] | 1900-06-08 | Q2-1900 | [21 empty] | Not Gated |  |  |  | Lattice ext | 108 | 0 | No Forcast Date | 0 Not Gated UTS 108 No Forcast Date | 0 |  | Lattice | 20 | Lattice ext | 24 |  |  |  |  | - | - | - | - | - | - | - | - | - | -
| TCNxxxx | Site name | Cork | 108 | UID203 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Modular Monopole | 12 |  |  |  |  | Cork County | 2 |  | 2023-09-27 | LOC | RC | 2500 | 2023-09-27 | 2023-09-29 | Yes |  | 2023-11-10 |  |  | Yes | Application | Yes | 2023-11-15 |  |  | Amber | FI | Appeal | 2023-11-20 | 2023-11-23 | 2023-11-27 | 236375 | [8 empty] | 2024-01-30 | 2024-01-30 | REFUSED | 0 | 2024-03-05 |  | TL APPEAL | 2025 | 2024-02-26 | 2024-02-26 |  | 319135 | 2025-02-20 |  | 2024-09-25 | REFUSED | 2025-02-20 | Refusal | 2024-09-25 | REFUSED | 0 | Refused | Part A (108) |  |  |  | Archive | 3rd Appl - failed | [57 empty] | 2 | 1 |  | 2021-11-04 | [7 empty] | 1 | 2029-01-01 | [5 empty] | No FP & Demand | 2029-01-01 | 2025-02-20 | Wooden Pole Replacement - ACA | 2025-02-27 | [45 empty] | 2025-03-09 | [5 empty] | 2025-04-28 | [12 empty] | 2025-05-08 | [11 empty] | - | 2025-06-07 | 0 | [16 empty] | 2026-03-24 | Q1-2026 | [21 empty] | Not Gated |  |  |  | Modular Monopole | 108 | Wooden Pole Replacement - ACA | No Forcast Date | Wooden Pole Replacement - ACA Not Gated UTS 108 No Forcast Date | 0 |  | Wooden Pole | 12 | Modular Monopole | 12 |  |  |  |  | - | - | 68 | 2.2667 | 307 | 10.2333 | 2024-02-26 | 212 | 7.0667 | 2024-09-25
| TMHxxxx | Site name | Donegal | 108 | UID024 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Mast | 15 | Lattice | 20 |  |  |  | Poor coverage, oppt with MNO? 30mtr only option? | Donegal County | 2 |  | 2020-02-10 | Entrust | OL | 2500 | 2020-02-10 | 2020-02-07 |  |  | 2020-05-07 |  |  | Yes | Application | Yes | Yes |  |  | Green |  | Appeal | 2021-05-31 | 2021-05-31 | Yes | 2151119 | No | - | - | - | - | - | - | - | 2021-08-09 | 2021-07-22 | GRANT |  | 2021-09-01 | 2021-09-01 | GRANT | 2021 | 2021-08-18 | [7 empty] | 2021-09-01 | Grant | 2021-09-01 | GRANT | 2026-08-31 | Final Grant | Part A (16) |  |  |  | Complete | 1st Appl - success |  |  |  |  | 2021-01-08 | [49 empty] | - |  |  | 2 | 0 | [9 empty] | 2 |  | 2026-01-01 |  | 2026-01-01 |  |  | FP / No Demand | 2026-01-01 | 2021-09-01 |  | 2025-11-01 | [76 empty] | - |  | 0 | [16 empty] | 2026-04-30 | Q2-2026 | [21 empty] | Not Gated |  |  |  | Lattice | 108 | 0 | No Forcast Date | 0 Not Gated UTS 108 No Forcast Date | 0 |  | Lattice Mast | 15 | Lattice | 20 |  |  |  |  | - | - | 52 | 1.7333 | 93 | 3.1 | - | - | - | -
| TLKxxxx | Site name | Dublin | 108 | UID026 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Tower | 15 | Lattice ext | 20 |  |  | Extension |  | South Dublin | 2 |  | Yes | LOC | OL | - | 2019-10-24 | 2019-10-30 |  |  | 2019-10-31 |  |  | Yes | Appeal | Yes | 2020-06-18 |  |  | Amber |  | Appeal | 2020-02-14 | 2020-02-14 | 2020-02-18 | SD20A/0042 | [8 empty] | 2020-04-29 | 2020-04-29 | REFUSED | 11 | 2020-06-22 | 2020-06-22 | TL APPEAL | 2020 | 2020-05-26 | 2020-06-19 |  | 307377 | 2020-10-22 |  | 2020-10-01 | GRANT | 2020-10-01 | Grant | 2020-10-01 | GRANT | 2025-09-30 | Final Grant | Part A (18) |  | Yes |  | Complete | 1st Appl - success | [10 empty] | Y |  | Colour Scheme & Landscaping Plan Required. | No | No | YES | YES | No | No | No | [5 empty] | No | No |  |  | n/a | n/a | [21 empty] | 2021-02-17 | Timed out | 2 |  | existing | 2 | 2 | 2021-01-01 |  | 2022-01-01 | 2021-10-19 | [5 empty] | 0 | [6 empty] | FP & Demand | - | 2020-10-01 |  | 2020-10-08 | 2020-11-20 | RFI | [5 empty] | Yes | [37 empty] | 2020-10-18 | [5 empty] | 2020-12-07 | [12 empty] | 2020-12-17 | [11 empty] | Timed out | 2021-01-16 | 0 | [16 empty] | 2021-09-07 | Q3-2021 | 2021-09-07 |  |  |  | n/a | [15 empty] | TLKxxxx | Live | TLKxxxx | 2021-09-07 | 2021-09-07 | Lattice ext | 108 | 0 | Q3-2021 | 0 Live UTS 108 Q3-2021 | RFI | Site name | Lattice Tower | 15 | Lattice ext | 20 |  |  |  |  | - | - | 75 | 2.5 | 230 | 7.6667 | 2020-06-19 | 104 | 3.4667 | 2020-10-01
| TGYxxxx | Site name | Laois | 108 | UID027 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 10 | Monopole | 21 |  |  | Not Adjacent |  | Laois County | 2 |  | Yes | Charterhouse | RC | 2500 | 2020-03-02 | 2020-09-04 |  |  | 2020-09-14 | [8 empty] | Amber | FI |  | 2020-09-18 | 2020-09-18 | Yes | 20477 |  |  | 2020-10-30 | 2021-04-29 | 2021-04-22 |  |  |  | 2021-09-03 | 2021-08-12 | GRANT | 0 | 2021-10-08 |  | TL APPEAL | 2022 | 2021-09-08 | 2021-09-08 |  | 311332 | 2022-01-20 |  | 2022-04-13 | GRANT | 2022-04-13 | Grant | 2022-04-13 | GRANT | 2027-04-12 | Final Grant | Part A (19) |  | 2022-07-01 | Yes | Complete | 1st Appl - success | [5 empty] | FIR | 2021-04-01 |  |  |  |  | Further FI to be submitted |  | No | No | No | No | No | YES | No | [5 empty] | No | NB Surface Water |  |  | n/a | n/a | n/a | n/a | n/a | n/a | [17 empty] | 2023-02-15 | 2023-03-29 | 2 |  |  | 3 | 1 |  | 2023-09-21 | [7 empty] | 2 | 2028-01-01 |  |  | 2030-01-01 |  |  | FP & Demand | 2028-01-01 | 2022-04-13 |  | 2022-04-20 | 2022-07-08 | RFI | [5 empty] | Yes | [33 empty] | Yes |  |  |  | 2022-04-30 | [5 empty] | 2022-06-19 | [12 empty] | 2022-06-29 | [11 empty] | 2023-03-29 | 2022-07-29 | 0 | [7 empty] | Yes | [8 empty] | 2023-09-21 | Q3-2023 | 2023-09-21 |  | Gate to be erected and fence to be repaired and exiting structure to be removed? |  | Yes | Wooden Pole | 2024-11-28 | [13 empty] | TGYxxxx | Live | TGYxxxx | 2023-09-21 | 2023-09-21 | Monopole | 108 | 0 | Q3-2023 | 0 Live UTS 108 Q3-2023 | RFI | Site name | Wooden Pole | 10 | Monopole | 21 |  |  |  |  | - | - | 328 | 10.9333 | 572 | 19.0667 | 2021-09-08 | 217 | 7.2333 | 2022-04-13
| TLKxxxx | Site name | Cork | 108 | UID135 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Monopole | 21 |  |  |  | WP TLM G, TI | Cork County | 3 |  | 2022-08-16 | Charterhouse | Quayline | - | 2022-08-16 | 2022-08-25 | Yes |  | 2022-09-02 |  |  | No | - | - | - | - |  | Red | Yes | - | 2022-09-09 | 2022-09-09 | 2022-10-03 | 22618 | No | - | - | - | - | - | - | - | 2023-03-10 | 2022-11-24 | REFUSED |  | 2023-04-14 |  | TL APPEAL | 2023 | 2022-12-21 | 2022-12-21 |  | 321229 (old case: 315401) | 2025-11-12 | Refusal |  |  | 2025-11-12 | Refusal |  |  | 0 | Appeal | 3A |  |  |  | Current | 1st Appl | [5 empty] | TJ | 2022-05-01 |  | Cellnex |  |  | Orignal ABP Ref: 315401 quashed by HC as part of JR, remitted and reactivated case 321229 - ABP letter 15/11/24. | [45 empty] | 1 | 1 |  | 2024-04-22 | [7 empty] | 0 | [6 empty] | No FP & Demand | - | 2025-11-12 | 2027-01-01 | 2026-09-01 | 2026-09-08 | [75 empty] | - | [18 empty] | 46453 | Q1-2027 | [20 empty] | TLKxxxx | Live | TLKxxxx | 2027-03-07 |  | Monopole | 108 | 46388 | Q1-2027 | 46388 Live UTS 108 Q1-2027 | 0 | Site name | Wooden Pole | 12 | Monopole | 21 | 2024-03-25 | Complete | 2024-10-08 | Remitted | 197 | 6.5667 | 76 | 2.5333 | - | - | 2022-12-21 | - | - | -
| TLMxxxx | Site name | Roscommon | 108 | UID029 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 10 | Lattice | 20 | Lattice Tower | 20 |  |  | Roscommon County | 2 |  | 2020-08-31 | Charterhouse | OL | 2500 | 2020-08-31 | 2020-09-22 | Yes |  | 2021-03-05 |  |  | Yes | FI | Yes |  |  |  | Amber | FI | Appeal | 2021-03-19 | 2021-03-19 | Yes | 21140 | No | - | 2021-05-13 | 2022-02-21 | 2022-02-16 | - | - | - | 2022-04-04 | 2022-04-01 | REFUSED | 13 | 2022-05-09 |  | TL APPEAL | 2023 | 2022-04-28 | 2022-04-27 |  | 313434 | 2023-10-30 |  | 2023-08-14 | GRANT | 2023-10-30 | Refusal | 2023-08-14 | GRANT | 2028-08-12 | Final Grant | Part A (20) |  | Yes |  | Complete | 1st Appl - success | [5 empty] | TJ | 2022-02-01 | [5 empty] | 1. Build according to plans. 2. Make structure available to all telcos. 3. Reinstate land after cessation of use. 4. Keep the boundary trees and replace if they die. 5. Landscaping plan -agree details of boundary trees prior to build start. 6.Remove existing wooden pole within 6 months of new structure becoming operational. 7. Colour scheme required. 8. No adverisements on site. 9. Build only during office hours (8am-7pm mon-fri, 8am-2pm sat). | No | No | YES | YES | No | No | No | [5 empty] | No | 4. Existing boundary trees to be retained and replaced if they die. 5. Mix of native hedge planting along northern boundary such as Ilex aquilfolium (common holly) and Crataegus monogyna (common hawthorn) or similar available 6. Remove existing wooden pole within 6 months of new structure becoming operational. 7. Standard colour scheme (green palisade fencing) |  |  | n/a | n/a | 2023-09-12 | 2023-10-23 | 2023-09-12 | 2023-10-23 | [17 empty] | 2023-09-12 | 2023-10-23 | 2 |  |  | 2 | 1 |  | 2021-09-09 | [7 empty] | 1 | 2028-01-01 | [5 empty] | FP & Demand | 2028-01-01 | 2023-10-30 |  | 2023-11-06 | 2023-08-25 | RFI | 101 | Replacement | 20m Tower |  | GSM 01 | Yes | N/A |  | Yes | [24 empty] | Yes | 2023-09-04 | 2023-09-04 | Not Required | - | - | - |  | - |  | 2023-08-30 | 2023-08-29 | Delmec | 2023-08-31 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 4 | 2023-09-29 | Assumed ESB Supply Solution issued with DD N.B. Permanent Solution Required Before Build |  | 2023-09-29 |  | 2023-09-29 | n/a | 2023-09-29 |  | 2024-06-12 |  | 2023-10-09 | 2024-06-12 |  | N.B. | - | - | - | - | Required | - |  |  | 2023-10-23 | 2023-11-08 | 2024-07-22 | 2024-07-22 | 2024-08-23 | 2024-10-07 | 2024-10-11 |  |  |  |  | 2024-10-07 | 2024-10-11 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-10 | Q4-2024 | 2024-12-09 |  |  |  | Yes | Wooden Pole - VF Equipment to be Removed | [14 empty] | TLMxxxx | Live | TLMxxxx | 2024-12-10 | 2024-12-09 | Lattice | 108 | 0 | Q4-2024 | 0 Live UTS 108 Q4-2024 | RFI | Site name | Wooden Pole | 10 | Lattice | 20 |  |  |  |  | - | - | 378 | 12.6 | 878 | 29.2667 | 2022-04-27 | 474 | 15.8 | 2023-08-14
| TMOxxxx | Site name | Galway | 108 | UID030 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Monopole | 20 | Monopole | 24 |  |  |  |  | Galway County | 2 | 2027-05-02 |  | LOC | RC | 2500 | 2027-05-02 | [12 empty] | Green |  |  | 2027-07-01 | [11 empty] | 2027-08-30 |  |  |  | 2027-10-04 |  |  | 2028 |  |  |  |  | 2028-05-30 | Refusal |  |  | 2028-05-30 | Refusal |  |  | 0 |  | 3B |  |  |  | Forecast | 1st Appl | Y |  | OPW | Subject to Agreement - Current Tetra Mast facilitating Lease Up | [53 empty] | 1 | 0 | existing | existing | [7 empty] | 1 |  |  |  | 2030-01-01 |  |  | No FP / No Demand | 2030-01-01 | 2028-05-30 | OPW TBC | [46 empty] | 1900-01-09 | [5 empty] | 1900-02-28 | [12 empty] | 1900-03-10 | [11 empty] | - | 1900-04-09 | 0 | [16 empty] | 1900-06-08 | Q2-1900 | [21 empty] | Not Gated |  |  |  | Monopole | 108 | OPW TBC | No Forcast Date | OPW TBC Not Gated UTS 108 No Forcast Date | 0 |  | Monopole | 20 | Monopole | 24 |  |  |  |  | - | - | - | - | - | - | - | - | - | -
| TLMxxxx | Site name | Cork | 108 | UID031 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Monopole | 25 | Lattice | 30 |  |  |  | no demand, developed for TI, VF | Cork County | 1 |  | 2021-11-19 | Charterhouse | Quayline | - | 2021-11-19 | 2021-12-02 | Yes |  | 2021-12-08 | [8 empty] | Amber |  |  | 2021-12-13 | 2021-12-13 | Yes | 217340 | No | - | 2022-02-15 | 2022-08-14 | 2022-07-29 | - | - | - | 2022-09-11 | 2022-08-29 | GRANT |  | 2022-10-14 | 2022-10-14 | GRANT | 2022 | 2022-09-25 | [7 empty] | 2022-10-14 | Grant | 2022-10-14 | GRANT | 2027-10-13 | Final Grant | 3f |  |  |  | Complete | 1st Appl - success | [5 empty] | TJ | 2021-07-01 | [6 empty] | No | No | No | No | No | YES | No | [5 empty] | No | N.B. Surface Water | [27 empty] | - |  |  | 1 | 0 |  | existing | [7 empty] | 1 |  |  |  |  | 2029-01-01 |  | FP / No Demand | 2029-01-01 | 2022-10-14 | On Hold - ROI | [46 empty] | 1900-01-09 | [5 empty] | 1900-02-28 | [12 empty] | 1900-03-10 | [11 empty] | - | 1900-04-09 | 0 | [16 empty] | 1900-06-08 | Q2-1900 | [21 empty] | Not Gated |  |  |  | Lattice | 108 | On Hold - ROI | No Forcast Date | On Hold - ROI Not Gated UTS 108 No Forcast Date | 0 |  | Monopole | 25 | Lattice | 30 |  |  |  |  | - | - | 259 | 8.6333 | 305 | 10.1667 | - | - | - | -
| TLKxxx | Site name | Cavan | EED | UID032 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Monopole | 18 |  |  | Option A |  | Cavan County | 3 |  | Yes | Charterhouse | OL | 2500 | 2021-02-01 | 2020-10-19 |  |  | 2021-03-19 |  |  | Yes | FI | No |  |  |  | Red |  | Appeal | 2021-04-02 | 2021-04-02 | Yes | 21206 | [8 empty] | 2021-06-11 | 2021-06-02 | REFUSED | 0 | 2021-07-16 |  | TL APPEAL | 2021 | 2021-06-29 | 2021-06-25 |  | 310641 | 2021-10-28 |  | 2021-12-20 | GRANT | 2021-12-20 | Refusal | 2021-12-20 | GRANT | 2026-12-19 | Final Grant | Part A (21) |  | Yes |  | Complete | 1st Appl - success | [12 empty] | 2. Landscaping scheme to be submitted and agreed with LPA in writing prior to commencement of the development. 3. Surface water drainage to comply with LPA requirements 4. Colour scheme to be agreed with LPA in writing prior to commencement of the development. 5. Construction hours limited to 0700 to 1900 Mon to Fri and 0800 to 1400 on Sat only. 8. AWL to be fitted with details to be submitted and agreed with LPA in writing prior to commencement of the development. 9. Construction management Plan to be submitted including traffic management, noise amangement and waste management. 10. Developer shall lodge a cash deposit, bond or other security to secure reinstatement of the site with an agreement. Form and amount to be agreed between developer and LPA. [Bond confirmed as €6000] | YES | No | YES | YES | No | YES | No | [5 empty] | No | NB Surface water | [6 empty] | 2022-07-19 | 2022-09-13 | [17 empty] | 2022-05-09 | Bond wording only | 5 |  |  | 3 | 2 | 2023-01-01 | 2022-12-12 | [7 empty] | 1 |  |  |  | 2030-01-01 |  |  | FP & Demand | 2030-01-01 | 2021-12-20 |  | 2021-12-27 | 2022-02-16 | RFI | [5 empty] | Yes | [37 empty] | 2022-01-06 | [5 empty] | 2022-02-25 | [12 empty] | 2022-03-07 | [11 empty] | Bond wording only | 2022-04-06 | 0 | [16 empty] | 2022-12-12 | Q4-2022 | 2022-12-12 |  |  |  | Yes | Wooden Pole | 2023-10-17 | [13 empty] | TLKxxx | Live | TLKxxx | 2022-12-12 | 2022-12-12 | Monopole | EED | 0 | Q4-2022 | 0 Live UTS EED Q4-2022 | RFI | Site name | Wooden Pole | 12 | Monopole | 18 |  |  |  |  | - | - | 61 | 2.0333 | 262 | 8.7333 | 2021-06-25 | 178 | 5.9333 | 2021-12-20
| TCxxxx | Site name | Mayo | EED | UID034 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Mast | 15 | Lattice | 20 |  |  |  |  | Mayo County | 3 |  | 2022-07-27 | Charterhouse | focus + | - | 2022-07-27 | 2022-08-18 |  |  | 2022-09-25 | [8 empty] | Amber |  |  | 2022-09-29 | 2022-09-29 | 2022-10-03 | 22858 | No | - | - | - | - | - | - | - | 2022-12-01 | 2022-11-23 | GRANT | 0 | 2022-12-24 | 2022-12-24 | GRANT | 2023 | 2022-12-20 | [7 empty] | 2022-12-24 | Refusal | 2022-12-24 | GRANT | 2027-12-23 | Final Grant | Part A (22) |  |  |  | Complete | 1st Appl - success | [13 empty] | No | No | No | No | No | No | No | [5 empty] | No | N.B. Surface Water | [30 empty] | 3 | 0 | [9 empty] | 3 | 2027-01-01 |  |  | 2028-01-01 | 2031-01-01 |  | FP / No Demand | 2027-01-01 | 2022-12-24 | [37 empty] | Yes | [9 empty] | 1900-01-09 | [5 empty] | 1900-02-28 | [12 empty] | 1900-03-10 | [11 empty] | - | 1900-04-09 | 0 | [16 empty] | 1900-06-08 | Q2-1900 | [21 empty] | Not Gated |  |  |  | Lattice | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | Lattice Mast | 15 | Lattice | 20 |  |  |  |  | - | - | 55 | 1.8333 | 86 | 2.8667 | - | - | - | -
| TDUxxxx | Site name | Mayo | EED | UID033 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Mast | 15 | Monopole | 24 |  |  |  |  | Mayo County | 3 | 2024-11-11 | 2024-09-18 | Charterhouse | DW |  | 2024-09-18 | 2024-10-07 | Yes | 1 | 2024-11-04 | 2024-06-25 | 2024-07-25 | Yes | Application | 2024-12-16 |  |  |  | Amber |  | Appeal | 2025-01-10 | [11 empty] | 2025-03-11 |  |  |  | 2025-04-15 |  |  | 2026 |  |  |  |  | 2026-04-10 | Refusal |  |  | 2026-04-10 | Refusal |  |  | 0 |  | Part A (22) |  |  |  | Forecast | Plan B | [57 empty] | 4 | 0 | [9 empty] | 4 | 2027-01-01 | 2026-01-01 |  | 2028-01-01 | 2031-01-01 |  | No FP / No Demand | 2026-01-01 | 2026-04-10 | [47 empty] | 1900-01-09 | [5 empty] | 1900-02-28 | [12 empty] | 1900-03-10 | [11 empty] | - | 1900-04-09 | 0 | [16 empty] | 1900-06-08 | Q2-1900 | [21 empty] | Not Gated |  |  |  | Monopole | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | Lattice Mast | 15 | Monopole | 24 |  |  |  |  | - | - | - | - | - | - | - | - | - | -
| TKKxxxx | Site name | Longford | EED | UID363 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Rooftop Guy Pole | 3.5 | Lattice | 20 |  |  |  |  | Longford County | 1 |  | 2020-03-02 | Charterhouse | RC | 2500 |  | 2020-11-24 |  |  | 2021-03-17 |  |  | Yes | FI |  |  |  |  | Red | FI | Appeal | 2021-03-31 | 2021-03-31 | 2021-04-08 | 2195 |  |  | 2021-05-26 | 2021-11-25 | 2021-11-25 |  |  |  | 2021-12-30 | 2021-12-16 | Refused |  | 2022-02-03 |  | TL APPEAL | 2023 | 2022-01-12 | 2021-01-19 |  | 312528 | 2022-05-24 |  | 2023-03-20 | REFUSED | 2023-03-20 | Refusal | 2023-03-20 | REFUSED | 0 | Refused | Part A (88) |  |  |  | Archive | 1st Appl - failed | [8 empty] | Cignal | [67 empty] | 2027-01-01 |  |  | 2026-09-01 | 2026-09-08 | [94 empty] | 46453 | [21 empty] | TKKxxxx | Live | TKKxxxx | 2027-03-07 |  | Lattice | EED | 0 | 0 | 0 Live UTS EED 0 | 0 | Site name | Rooftop Guy Pole | 3.5 | Lattice | 20 |  |  |  |  | - | - | 260 | 8.6667 | 719 | 23.9667 | 2021-01-19 | 790 | 26.3333 | 2023-03-20
| TWWxxxx | Site name | Cork | EED | UID020 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Mast | 12 | Monopole | 15 |  |  |  |  | Cork County | 1 |  | 2021-11-18 | Charterhouse | focus + | - | 2021-11-18 | 2021-11-23 | Yes |  | 2021-12-01 | [8 empty] | Amber | FI |  | 2021-12-13 | 2021-12-13 | Yes | 217341 | No | - | 2022-02-14 | 2022-12-13 | 2022-10-21 | - | - | - | 2022-11-25 | 2022-11-21 | GRANT | 0 | 2023-01-04 | 2023-01-04 | GRANT | 2023 | 2022-12-18 | [7 empty] | 2023-01-04 | Grant | 2023-01-04 | GRANT | 2028-01-03 | Final Grant | 3f |  | n/a - no demand |  | Complete | 1st Appl - success | [5 empty] | TJ | Jul 21 & Mar 22 | [6 empty] | No | No | No | No | No | No | No | [5 empty] | No | N.B. Surface Water | [30 empty] | 3 | 0 | [9 empty] | 3 | 2031-01-01 | 2028-01-01 |  | 2029-01-01 |  |  | FP / No Demand | 2028-01-01 | 2023-01-04 |  | 2028-02-08 | [45 empty] | 2028-02-18 | [5 empty] | 2028-04-08 | [12 empty] | 2028-04-18 | [11 empty] | - | 2028-05-18 | 0 | [16 empty] | 2028-07-17 | Q3-2028 | [21 empty] | Not Gated |  |  |  | Monopole | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | Lattice Mast | 12 | Monopole | 15 |  |  |  |  | - | - | 343 | 11.4333 | 387 | 12.9 | - | - | - | -
| TWWxxxx | Site name | Cavan | EED | UID037 |  | xxxxx | xxxxx | xxxxx | xxxxxx | No Structure | 10 | Monopole | 18 |  |  |  |  | Cavan County | 3 |  | 2023-06-13 | LOC | RC | 1000 | 2023-06-13 | 2023-07-13 | Yes |  | 2023-07-25 |  |  | Yes | Application | 2023-07-24 | 2023-08-01 |  |  | Amber |  | Appeal | 2023-07-31 | 2023-08-04 |  | 2360127 | [8 empty] | 2023-11-28 | 2023-09-20 | REFUSED | 74 | 2024-01-12 |  | TL APPEAL | 2024 | 2023-10-17 | 2023-10-17 |  | 318262 | 2024-10-11 | Grant | 2024-07-17 | REFUSED | 2024-10-11 | Grant | 2024-07-17 | REFUSED | 0 | Refused | Part A (25) |  |  |  | Archive | 2nd Appl - failed | [57 empty] | 1 | 0 | [9 empty] | 1 |  | 2029-04-01 |  |  |  |  | No FP / No Demand | 2029-04-01 | 2024-10-11 |  | 2029-04-01 | [76 empty] | - |  | 0 | [16 empty] | 2029-09-28 | Q3-2029 | [21 empty] | Not Gated |  |  |  | Monopole | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | No Structure | 10 | Monopole | 18 | 2022-01-14 | Complete | 2022-12-08 | Quashed | 328 | 10.9333 | 47 | 1.5667 | 348 | 11.6 | 2023-10-17 | 274 | 9.1333 | 2024-07-17
| TWHxxxx | Site name | Roscommon | EED | UID038 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Monopole | 24 | Monopole | 24 |  | WP TLM G, | Roscommon County | 1 |  | 2023-08-11 | LOC | RC | 2500 | 2023-08-11 | 2023-08-15 | Yes |  | 2023-09-12 |  |  | Yes | Application | 2023-09-08 | 2023-10-09 | - |  | Green | - | Appeal | 2023-10-06 | 2023-10-09 | 2023-10-11 | 2360167 | No |  | 2023-12-05 | 2024-06-04 | 2024-04-29 |  |  |  | 2024-05-29 | 2024-06-10 | GRANT | 1 | 2024-07-11 | 2024-07-15 | GRANT | 2025 |  |  |  |  | 2025-06-28 |  |  |  | 2025-06-28 | Grant | 2024-07-15 | GRANT | 2029-07-14 | Final Grant | Part A (26) |  | 2024-07-16 |  | Current | 2nd Appl - success | [8 empty] | 2023-11-10 |  |  |  | 1. The development shall be carried out strictly in accordance with the plans and particulars submitted to the Planning Authority on 11th October 2023 and the further information submitted on 14th May 2024, except as otherwise required in order to comply with the conditions of this permission as set out hereunder. No material change of use of the 24 metre monopole, antennas, dishes, associated equipment and cabinets shall be made without a prior grant of planning permission unless such change has the benefit of exempted development status, in accordance with Schedule 2 of the Planning & Development Regulations 2001 (as amended). 2. The transmission power output, antennae type, and mounting configuration shall be in accordance with the details submitted with this application and shall not be altered without a prior grant of planning permission, unless such alterations have the benefit of exempted development status, in accordance with Schedule 2 of the Planning & Development Regulations 2001 (as amended). 3. Within 6 months of the permanent cessation of use of the structures, all structures on site shall be removed at the applicants/developers own expense and the site shall be reinstated in accordance with a restoration plan to be submitted for the written agreement of the Planning Authority within three months of the date of the final grant of this permission. 4. Prior to commencement of development, the developer shall submit, for the written agreement of the Planning Authority, a detailed Construction Management Plan (to include traffic management proposals) for the proposed development. The traffic management proposals shall be informed by prior engagement with Roscommon County Council’s Roscommon Municipal District Co-Ordinator. The development shall thereafter be undertaken in accordance with the agreed details. 5. All surface water generated within in the site boundaries shall be collected and disposed of within the curtilage of the site. No surface water from roofs, paved areas or otherwise shall discharge onto the public road. 6. The Planning Authority shall be notified of any change of ownership or transfer to a new operator. Such notification shall be made within two months of the date of change of ownership or transfer. 7. Sound pressure levels generated by the development shall not exceed background levels when measured at any dwelling in the vicinity of the site. All sound measurements shall be carried out in accordance with ISO Recommendations 1996 “Assessment of noise with respect to community response” as amended by ISO Recommendations R 1996/1, 2 and 3 “Description and measurement of Environmental Noise” as appropriate. 8. The applicant/developer shall give the Planning Authority two weeks' notice in writing of intent to commence development on the site. | No | No | No | No | YES | YES | No | YES | No | No | No | No | YES | Highlighting Required Actions in relation to Compliance Requirements. Cond 3. Within 3 mths Final Grant - cessation plan to be sumbitted to LPA for when/if site ever ceases to be used as telcos site. Cond 4. CMP to include TMP & engagement required with LPAs Municipal District Co-Ord prior to finalising Traffic Management Plan for submission. Cond 8. Commencement Notice required Two Weeks prior to start on site. | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2024-07-26 | 2024-09-12 | 2024-07-26 | 2024-09-12 | n/a | n/a | 2024-07-26 | 2024-10-11 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2024-09-11 | 2024-10-03 | 2024-10-11 | 4 |  |  | 3 | 1 |  | 2021-09-09 | [7 empty] | 2 | 2027-01-01 |  |  | 2028-01-01 |  |  | FP & Demand | 2027-01-01 | 2024-07-11 |  | 2024-07-18 | 2024-06-12 | RFI | 103 | Replacement | Yes |  | GSM 02 | Yes | N/A | Yes | No | [11 empty] | No | - | - |  | - |  | 2024-06-26 | No | [5 empty] | No |  |  |  | - |  | No | N/A |  | N/A | 2024-07-28 | 2024-06-26 | TL | - | - | 2024-07-16 | 2024-09-16 | 3 | 2024-07-30 | Temp Power Supply Solution issued with DD | 1 | 2024-07-30 | 1 | 2024-07-30 | n/a | 2024-07-30 | 1 | 2024-08-08 |  | 2024-09-26 | 2024-08-09 | [10 empty] | 2024-10-11 | 2024-10-26 | 2024-10-21 |  |  | 2024-10-21 | 2024-10-25 |  |  |  |  | 2024-10-21 | 2024-10-25 | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-06 | Q4-2024 | 2024-12-06 |  |  |  | Yes | Wooden Pole - VF Equipment to be Removed | [14 empty] | TWHxxxx | Live | TWHxxxx | 2024-12-06 | 2024-12-06 | Monopole | EED | 0 | Q4-2024 | 0 Live UTS EED Q4-2024 | RFI | Site name | Wooden Pole | 12 | Monopole | 24 |  |  |  |  | - | - | 245 | 8.1667 | 280 | 9.3333 | - | - | - | -
| TCNxxxx | Site name | Kildare | EED | UID231 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Rooftop | 23.3 | Lattice | 30 |  |  |  | VC: FP for 24mtr grant | Kildare County | 1 |  | 2024-05-20 | LOC | RC |  | 2024-05-20 | 2024-07-01 | Yes | 2 | 2024-07-01 | 2024-05-29 | 2024-06-13 | [6 empty] | Amber |  | Appeal | 2024-06-26 | 2024-07-01 | 2024-07-02 | 2460599 | [8 empty] | 2024-08-25 | 2024-08-20 | GRANT | 0 | 2024-09-29 | 2024-10-02 | GRANT | 2025 |  |  |  |  | 2025-09-24 | Refusal |  |  | 2025-09-24 | Refusal | 2024-10-02 | GRANT | 2029-10-01 | Final Grant | Part B (43) |  | 2024-10-03 |  | Complete | 2nd Appl - success | Y | Long Lease | [11 empty] | YES | YES | No | No | No | No | No | No | No | No | No | No | No | No | 2024-10-07 | 2024-10-09 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2024-10-07 | 2024-10-09 | 1 |  |  | 2 | 1 |  | 2024-08-13 | [7 empty] | 1 |  |  |  |  | 2026-01-01 |  | FP & Demand | 2026-01-01 | 2024-09-24 |  | 2024-10-01 | 2024-08-21 | RFI |  | New Structure | 30m Tower |  | GSM 02 | Yes | 2nd GSM Headframe Available in TL Yard | 2024-09-03 | No | [11 empty] | No | - | - | - | - | - | - | [11 empty] | - | - | - |  | - | 2024-10-11 | 2024-08-28 | TL | - | - | 2024-09-04 | 2024-09-30 | 1 | 2024-09-23 | ESB Independent Power Supply Solution issued with DD | 1 | 2024-09-11 | 1 | 2024-09-11 | n/a | 2024-09-30 |  | 2024-11-18 | 2 | 2024-10-10 | 2024-11-19 | 2 | [9 empty] | 2024-10-09 | 2024-11-09 | 2024-12-11 |  |  |  |  | 2024-12-11 | 2024-12-20 |  |  | 2024-12-11 | 2024-12-20 | 2025-01-22 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2025-01-24 | 2025-01-24 | Q1-2025 | [20 empty] | TCNxxxx | Live | TCNxxxx | 2025-01-24 |  | Lattice | EED | 0 | Q1-2025 | 0 Live UTS EED Q1-2025 | RFI | Site name | Rooftop | 23.3 | Lattice | 30 |  |  |  |  | - | - | 50 | 1.6667 | 93 | 3.1 | - | - | - | -
| TMHxxxx | Site name | Kildare | EED | UID040 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Monopole | 18 |  |  | Not Adjacent |  | Kildare County | 3 |  | Yes | Entrust | OL | - | 2019-12-03 | 2019-12-10 |  |  | 2020-06-26 | [8 empty] | Green | FI |  | 2020-07-24 | 2020-07-24 | Yes | 20853 |  |  | 2020-09-21 | 2021-03-20 | 2021-03-19 |  |  |  | 2021-04-26 | 2021-04-07 | REFUSED |  | 2021-05-31 |  | TL APPEAL | 2021 | 2021-05-04 | 2021-05-04 |  |  | 2021-09-14 |  | 2021-06-30 | GRANT | 2021-06-30 | Grant | 2021-06-30 | GRANT | 2026-06-29 | Final Grant | Part A (27) |  | Yes |  | Complete | 1st Appl - success | [5 empty] | FIR | 2021-04-01 |  |  |  |  | 19/04/21: Change from 20m HD monopole to 18m Monopole S | Colour Scheme & Landscaping Plan Required. | No | No | YES | YES | No | No | No | [5 empty] | No | No | n/a | n/a | [23 empty] | 2021-12-10 | 2021-12-17 | 2 |  |  | 2 | 2 | 2022-08-12 |  | 2022-08-12 | 2022-02-09 | [5 empty] | 0 | [6 empty] | FP & Demand | - | 2021-06-30 |  | 2021-07-07 | 2021-10-04 | RFI | [5 empty] | Yes | [33 empty] | Yes |  |  |  | 2021-07-17 | [5 empty] | 2021-09-05 | [12 empty] | 2021-09-15 | [11 empty] | 2021-12-17 | 2021-10-15 | 0 | [7 empty] | Yes | [8 empty] | 2022-08-12 | Q3-2022 | 2022-08-12 |  | Wall footpath realignment? |  | Yes | Wooden Pole | 2022-08-12 | [13 empty] | TMHxxxx | Live | TMHxxxx | 2022-08-12 | 2022-08-12 | Monopole | EED | 0 | Q3-2022 | 0 Live UTS EED Q3-2022 | RFI | Site name | Wooden Pole | 12 | Monopole | 18 |  |  |  |  | - | - | 257 | 8.5667 | 341 | 11.3667 | 2021-05-04 | 57 | 1.9 | 2021-06-30
| TLKxxxx | Site name | Waterford | EED | UID188 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Mast | 12 | Monopole | 15 | Monopole | 16 |  |  | Waterford County | 1 |  | 2022-05-04 | Charterhouse | RC | - | 2022-05-04 | 2022-09-01 | Yes |  | 2022-09-16 |  |  | - | - | - | - | - |  | Red | FI | Appeal | 2022-09-16 | 2022-09-16 | Yes | 22993 | Yes | Site Notice | 2023-01-19 | 2023-07-18 | 2023-07-06 | - | - | - | 2023-08-20 | 2023-08-14 | GRANT | 2 | 2023-09-24 | 2023-10-09 | GRANT | 2024 | 2023-09-10 |  |  |  | 2024-09-24 |  |  |  | 2024-09-24 | Refusal | 2023-10-09 | GRANT | 2028-10-07 | Final Grant | Part A (100) |  | 2024-03-14 |  | Complete | 2nd Appl - success | [5 empty] | FIR | 2021-04-01 |  |  |  |  | 13/10 RR 18m* - FP Granted but with maximum overall height 16m, proposed extension to be submitted towards EOY 2023 for 2m extn to 18m 05/06: FI request - Change design to monopole and include Photomontage | NOTE - FP Application submitted for 18m Monopole - Final Grant was for 18m Monopole but with a Height Restriction of 16m. 1 (a) Proposed Development to be carried out in accordance with the plans and particulars lodged with the application on 25th November 2022, as amended by details submitted to the planning authority on 7th July 2023, except as otherwise may be required in order ot comply with the following conditions. 1 (b) The overall height of the monopole permitted shall not exceed 16m. Prior to the commencement of any development revised drawings making provision for same shall be submitted and agreed in writing with the planning authority. 1 (c) The monopole and any associated antennae permitted shall be painted dark green in accordance with details submitted to the planning authoirty on 7th July 2023. 2. In the event of the telecommunications structure and ancillary equipment hereby permitted ceasing to operate for a period of twelve months, the structure and ancillary equipment shall be removed. Details regarding the removal of the structure and reinstatement of the site shall be submitted to and agreed in writing within six months of the structures ceasing to operate and the site shall be reinstated in accordance with the agreed details. 3. The applicant shall provide and make available at reasonable terms the proposed telecommunications structure for the provision of mobile telecommunications antenna of third party licence mobile phone operators. | No | No | YES | No | No | No | No | No | No | No | No | No | No | FI - TL commited to painting the proposed structure dark green - suggest RAL 6028 The Final Planning Grant Cond 1 (b) requires monopole and any associated antennae permitted shall be painted dark green Prior to the commencement of any development revised drawings making provision for 16m Monopole painted Drak Green shall be submitted and agreed in writing with the planning authority. | n/a | n/a | n/a | n/a | 2024-07-24 | 2024-09-24 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2024-07-24 | 2024-09-24 | 1 |  |  | 3 | 1 |  | 2023-08-28 | [7 empty] | 2 | 2027-01-01 |  |  | 2031-01-01 |  |  | FP & Demand | 2027-01-01 | 2024-09-24 |  | 2024-10-01 | 2024-03-07 | RFI | 113 | Replacement | 16m* Monopole |  | Delmec | Ordered | Ordered | [13 empty] | Yes | Delmec | 2024-04-16 |  | 2024-05-16 | [9 empty] | - | - | - | - | - | - | - | - |  | 2024-09-27 | 2024-03-15 | Delmec | 2024-04-02 | 2024-04-09 | 2024-08-02 | 2024-10-27 | 3 | 2024-10-11 | TBC | 1 | 2024-10-11 | 1 | 2024-10-11 |  | 2024-10-11 | 1 | 2024-10-14 |  | 2024-11-06 | 2024-10-14 |  | Required | - | - | - | - | - | - |  |  | 2024-09-24 | 2024-12-06 | 2024-11-11 | 2024-11-11 | 2024-11-15 | 2024-11-11 | 2024-11-15 |  |  |  |  | 2025-01-20 | 2025-01-24 | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | Q1-2025 | [5 empty] | Lattice Tower - VF Hot Swap Required | [14 empty] | TLKxxxx | Live | TLKxxxx | 2025-02-11 |  | Monopole | EED | 0 | Q1-2025 | 0 Live UTS EED Q1-2025 | RFI | Site name | Lattice Mast | 12 | Monopole | 15 |  |  |  |  | - | - | 332 | 11.0667 | 388 | 12.9333 | - | - | - | -
| TGYxxxx | Site name | Kilkenny | EED | UID043 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Tower | 15 | Lattice | 20 |  |  | Not Adjacent |  | Kilkenny County | 2 |  | Yes | Charterhouse | OL | 2500 | 2020-02-10 | 2020-03-26 |  |  | 2020-04-15 | [8 empty] | Gre | FI |  | 2020-08-26 | 2020-08-26 | 2020-08-27 | 20563 |  |  | 2020-10-19 | 2021-04-18 | 2021-04-16 |  |  |  | 2021-05-16 | 2021-05-11 | GRANT | 0 | 2021-06-20 |  | TL APPEAL | 2022 | 2021-06-07 | 2021-06-08 |  | 310469 | 2021-10-11 |  | 2022-03-04 | GRANT | 2022-03-04 | Refusal | 2022-03-04 | GRANT | 2027-03-03 | Final Grant | Part A (28) |  | Yes | Yes | Complete | 1st Appl - success | [11 empty] | 23/07/20: Change of planner from LOC to JohnC |  | No | No | YES | YES | No | No | No | [5 empty] | No | No | [25 empty] | 2023-03-06 | 2023-03-30 | 3 |  |  | 3 | 1 |  | 2023-08-23 | [7 empty] | 2 | 2024-01-01 |  |  | 2028-01-01 |  |  | FP & Demand | 2024-01-01 | 2022-03-04 |  | 2022-03-11 | 2022-03-30 | RFI | [5 empty] | Yes | [33 empty] | Yes |  |  |  | 2022-03-21 | [5 empty] | 2022-05-10 | [12 empty] | 2022-05-20 | [11 empty] | 2023-03-30 | 2022-06-19 | 0 | [7 empty] | Yes | [8 empty] | 2023-08-23 | Q3-2023 | 2023-08-23 |  |  |  | Yes | Lattice Tower | [14 empty] | TGYxxxx | Live | TGYxxxx | 2023-08-23 | 2023-08-23 | Lattice | EED | 0 | Q3-2023 | 0 Live UTS EED Q3-2023 | RFI | Site name | Lattice Tower | 15 | Lattice | 20 |  |  |  |  | - | - | 258 | 8.6 | 555 | 18.5 | 2021-06-08 | 269 | 8.9667 | 2022-03-04
| TLKxxxx | Site name | Galway | EED | UID077 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Monopole | 15 | Monopole | 21 |  |  |  |  | Galway County | 2 |  | 2023-09-22 | Charterhouse | RC | 2500 | 2023-09-22 | 2023-10-10 |  |  | 2023-10-20 |  |  | Yes | FI |  |  |  |  | Green |  | Appeal | 2023-10-28 | 2023-10-28 | 2023-11-06 | 23/61320 |  |  | 2024-01-09 | 2024-07-08 | 2024-04-17 |  |  |  | 2024-05-17 | 2024-05-14 | GRANT | 6 | 2024-06-21 | 2024-06-24 | GRANT | 2025 | 2024-06-10 |  |  |  | 2025-06-16 |  |  |  | 2025-06-16 | Refusal | 2024-06-24 | GRANT | 2029-06-23 | Final Grant | 3f |  | 2024-07-09 |  | Complete | 1st Appl - success | [11 empty] | Ref 23/61292 Invalidated (Dwg) then Resubmitted 06 Nov 2023 under Ref 23/61320 | 1. The development shall be carried out and completed in accordance with the plans and particulars lodged with the application on the 6th of November 2023, and as amended by the plans and particulars received by the Planning Authority on the 17th of April 2024, except as may otherwise be required in order to comply with the following conditions. Where such conditions require points of detail to be agreed with the Planning Authority, these matters shall be the subject of written agreement prior to the works commencement and shall be implemented in accordance with the agreed particulars. 2. The proposed structure shall have a maximum height of 24m. 3. The transmitter power output, antenna type and mounting configuration shall be in accordance with the details submitted with this application and, notwithstanding the provisions of the Planning and Development Regulations 2001, and any statutory provision amending or replacing them, shall not be altered without a prior grant of planning permission. 4.The support structure, antennae and all ancillary structures should be demolished and removed from site if they become obsolete or are no longer required, and the site shall be reinstated on removal of the telecommunications structure and ancillary structures at the operators’ expense. 5. All public roads and footpaths shall be maintained free from dirt and debris during construction stage of the proposed development. All necessary measures shall be undertaken by the applicant to prevent the spillage or deposit of clay, rubble or other debris on adjoining lands during the course of the works. 6. The Applicant and any subsequent owners or operators of the installation shall inform the planning section of Galway County Council of impending transfer of installation to another owner or operator to facilitate the continuance of planning conditions. 7.(i)No material change of use of the structure shall be made without a prior grant of planning permission. (ii) Development described in Class 31 of Part 1 of Schedule 2 of the Planning and Development Regulations, 2001, as amended shall not be carried out within the site, without a prior grant of planning permission. 8.No advertisement or advertisement structure shall be erected or displayed on the structure or its appendages or within the curtilage of the site without a prior grant of planning permission. 9.(i) A system of independent monitoring of radiation levels from the mast shall be established/maintained and undertaken periodically to ensure compliance with such guidelines levels as may be set from time to time by the International Radiation Protection Association. (ii) The development shall comply with the terms and conditions of the public exposure guidelines of the international commission on non-ionizing radiation protection. 10. (i)The applicant/owner/operator shall provide and make available on reasonable terms other licensed mobile telecommunications operators to co-locate their antennae onto the existing structure. (ii) Adequate space to be allowed on site by the applicant for an additional equipment container by a second telecommunications operator should such be required. 11. A low intensity fixed red obstacle light shall be fitted as close to the top of the mast as practicable and shall be visible from all angles in azimuth unless otherwise agreed in writing with the Planning Authority. 12.(i)All surface water shall be disposed of on-site to appropriately sizes soakaways in accordance with BRE Digest 365 or equivalent and shall not flow on the road or adjoining property. (ii)The development shall not impair existing land or road drainage. | N | YES | N | N | N | N | N | N | N | N | N | N | N | Proposed Planting North West Boundary per Sheet 06 Dwg No TGY6020-PL-05 however no Landscaping Plan required. Existing 15m Monopole to be Removed. | [30 empty] | 1 | 0 | [9 empty] | 1 |  |  | 2028-01-01 | 2028-01-01 |  |  | FP / No Demand | 2028-01-01 | 2025-06-16 |  | 2028-02-08 | [45 empty] | 2028-02-18 | [5 empty] | 2028-04-08 | [12 empty] | 2028-04-18 | [11 empty] | - | 2028-05-18 | 0 | [16 empty] | 2028-07-17 | Q3-2028 | [21 empty] | Not Gated |  |  |  | Monopole | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | Monopole | 15 | Monopole | 21 |  |  |  |  | - | - | 199 | 6.6333 | 240 | 8 | - | - | - | -
| TLMxxxx | Site name | Westmeath | EED | UID220 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Monopole | 15 |  |  |  |  | Westmeath County | 4 | 2024-12-02 | 2024-10-21 | Charterhouse | RC | 1000 | 2024-10-21 | 2024-10-25 | Yes | 1 | 2024-11-04 | 2024-09-25 | 2024-11-06 | Yes | Application | 2024-12-16 |  |  |  | Red |  | Appeal | 2025-01-31 | [11 empty] | 2025-04-01 |  |  |  | 2025-05-06 |  |  | 2026 |  |  |  |  | 2026-05-01 | Refusal |  |  | 2026-05-01 | Refusal |  |  | 0 |  | Part B (39) |  |  |  | Forecast | 2nd Appl | [57 empty] | 1 | 0 | [9 empty] | 1 |  | 2027-01-01 |  |  |  |  | No FP / No Demand | 2027-01-01 | 2026-05-01 |  | 2026-11-01 | [45 empty] | 2026-11-11 | [5 empty] | 2026-12-31 | [12 empty] | 2027-01-10 | [11 empty] | - | 2027-02-09 | 0 | [16 empty] | 2027-04-10 | Q2-2027 | [21 empty] | Not Gated |  |  |  | Monopole | EED | 0 | No Forcast Date | 0 Not Gated UTS EED No Forcast Date | 0 |  | Wooden Pole | 12 | Monopole | 15 |  |  |  |  | - | - | - | - | - | - | - | - | - | -
| TMOxxxx | Site name | Wexford | EED | UID047 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Lattice Tower | 15 | Lattice | 20 |  |  | Not Adjacent |  | Wicklow County | 3 |  | Yes | LOC | OL | 2500 | 2019-11-04 | 2020-04-23 |  |  | 2021-03-02 |  |  | Yes | Application |  | 2021-01-12 |  |  | Red |  | Appeal | 2021-03-16 | 2021-03-16 | 2021-03-18 | 21286 | [8 empty] | 2021-05-18 | 2021-05-12 | GRANT | 0 | 2021-06-18 | 2021-06-18 | GRANT | 2021 | 2021-06-08 | [7 empty] | 2021-06-18 | Refusal | 2021-06-18 | GRANT | 2026-06-17 | Final Grant | Part A (30) |  | Yes |  | Complete | 1st Appl - success | [12 empty] | The lattice support structure extension, antennas and cabinets shall be grey in colour. | No | No | NB | No | No | No | No | [5 empty] | No | No |  |  | n/a | n/a |  |  | n/a | n/a | [17 empty] | n/a | n/a | 1 |  |  | 2 | 1 | 2022-04-15 |  | 2022-04-15 | [6 empty] | 1 |  |  |  | 2029-01-01 |  |  | FP & Demand | 2029-01-01 | 2021-06-18 |  | 2021-06-25 | 2021-07-05 | RFI | [5 empty] | Yes | [37 empty] | 2021-07-05 | [5 empty] | 2021-08-24 | [12 empty] | 2021-09-03 | [11 empty] | n/a | 2021-10-03 | 0 | [16 empty] | 2022-04-15 | Q2-2022 | 2022-04-15 |  |  |  | Yes | Wooden Pole | 2022-06-24 | [13 empty] | TMOxxxx | Live | TMOxxxx | 2022-04-15 | 2022-04-15 | Lattice | EED | 0 | Q2-2022 | 0 Live UTS EED Q2-2022 | RFI | Site name | Lattice Tower | 15 | Lattice | 20 |  |  |  |  | - | - | 57 | 1.9 | 94 | 3.1333 | - | - | - | -
| TLMxxxx | Site name | Kildare | EED | UID177 |  | xxxxx | xxxxx | xxxxx | xxxxxx | Wooden Pole | 12 | Modular Monopole | 12 |  |  |  | WP TLM red, 3 sector. No access | Kildare County | 4 |  | 2020-08-07 | Charterhouse | OL | 1000 | 2020-08-07 | 2020-10-05 |  |  | 2020-12-04 | [8 empty] | Red | FI | Appeal | 2020-12-11 | 2020-12-11 | Yes | 201561 | No | - | 2021-02-16 | 2021-08-15 | 2021-08-12 | - | - | - | 2021-08-15 | 2021-09-02 | REFUSED | 3 | 2021-09-19 |  | TL APPEAL | 2022 | 2021-09-29 | 2021-09-29 |  | 311525 | 2022-02-10 |  | 2022-02-01 | GRANT | 2022-02-01 | Refusal | 2022-02-01 | GRANT | 2027-01-31 | Final Grant | Part A (94) |  | Yes | Yes | Complete | 1st Appl - success |  |  |  |  | 2021-01-30 | FIR | 2021-04-01 |  |  |  |  | Limited Ground Space - Site Survey completed | Details of proposed colour scheme to be agreed with LPA prior to commencement of development. Aircraft Warning Light to be installed - this requirement to be submitted to IAA for review. | No | YES | YES | No | No | No | No | [5 empty] | No | No | [6 empty] | n/a | n/a | [17 empty] | 2022-09-05 | 2022-09-15 | 2 |  |  | 2 | 1 |  | 2021-12-02 | [7 empty] | 1 | 2026-01-01 | [5 empty] | FP & Demand | 2026-01-01 | 2022-02-01 | On Hold - ROI | 2025-10-01 | 2025-10-08 | [44 empty] | 2025-10-11 | [5 empty] | 2025-11-30 | [12 empty] | 2025-12-10 | [11 empty] | 2022-09-15 | 2026-01-09 | 0 | [16 empty] | 2026-03-10 | Q1-2026 | [20 empty] | TLMxxxx | Live | TLMxxxx | 2026-03-10 |  | Modular Monopole | EED | On Hold - ROI | Q1-2026 | On Hold - ROI Live UTS EED Q1-2026 | 0 | Site name | Wooden Pole | 12 | Modular Monopole | 12 |  |  |  |  | - | - | 265 | 8.8333 | 417 | 13.9 | 2021-09-29 | 125 | 4.1667 | 2022-02-01
Formulas:
RR = IF([LOC]="Grant",[MS]+1825,0)
AP = IF((MIN([RH]:[RH]))=0,"-",(MIN([RH]:[RH])))
AP = [RH]
FP Final Decision Forecast = [Forecast FP Final Decision Date]
Gating = [FP Final Decision Forecast]+7
Gating = [SA]+7
Forecasted ICDD Date = [Gating]+10
Forecasted ICDD Date = [MS]-30
MS = IF([TS]="Yes",[MS],[Forecasted ICDD Date]+50)
MS = [Gating]+30
Notifications = [MS]+10
N.B. Same Date as FP Compliance = IF([LOC]=0,"-",[LOC])
Construction = [Notifications]+30
Start on Site = MIN([TS],[TS],[TS],[TS],[TS])
Forecast RFI Date = IF([Finance]="Live",IF([MS]>1000,[MS],""),"")
RFI Actual = IF([Finance]="Live",IF([MS]>1000,[MS],""),"")
SA = [AP]
Appeal Submission Date = IF([LOC]="",IF([LOC]="","-",[LOC]),[LOC])
ABP Final Decision Date = IF([MS]=0,"-",[MS])
LOC = [LOC]-60
LPA Initial Decision Date Forecast = [LOC]+60
LPA Final Decision Date Forecast = [LPA Initial Decision Date Forecast]+35
LPA Final Decision Date Forecast = ([MS]+31)
Forecast ABP Final Decision Date = [LPA Final Decision Date Forecast]+360
Forecast ABP Final Decision Date = [LPA Initial Decision Date Forecast]+274
Forecast FP Final Decision Date = [Forecast ABP Final Decision Date]
SB = [SB]+15
Note on CB5: HOP only required once Demand present and proceeds to D&C
Note on CD5: Forecast - application to be submitted in future Current - application ongoing (includes where refused but pending re-appl decision) Complete - application achieved planning Archive - application refused/withdrawn (may have new row for re-application)
Note on HH12: Stuart Armstrong: V. Constrained Site - Confirm site NOT buildable 28/03/2024 Site to be redesigned for Slimline solution in available space inside eir site boundary.
Note on IR12: ESB Supply TBC
Note on JB12: ESB OHL to be removed to stand structure TBC
Note on HH14: Require eir to confirm land ownership Spoil to be removed before DCP /SI Survey can be carried out DCP TBC
Note on EQ16: Tag
Note on FK16: 06/12/2023 VF SRF 07/09/2023 Part Gated eir Mobile
Note on IR16: ROL TMP Approved 14/02/2024
Note on FA30: Tag
Note on HY33: A/W ESB Diversion Solution
Note on JB33: ESB Outage Confirmed for 05/12/2024
Note on BG42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cellnex
Note on JB42: ESB Outage Confirmed for 03/12/2024
Note on JB43: AWL Required
Note on FC45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 operator tower solution
Note on IZ45: Only 2 Days Work o/s - TBC

## Sheet1 (hidden)
RFI
| 2024-01-01 | 2025-01-01 | 2026-01-01 | 2027-01-01 | 2028-01-01 | 2029-01-01 | 2030-01-01 | 2031-01-01
f/c RFI | 3 | 3 | 4 | 6 | 4 | 2 | 0 | 0
Submitted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initial Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refused | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 0
Appeal | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Final Grant | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 0
Withdrawn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0
| 3 | 3 | 4 | 6 | 4 | 2 | 0 | 0